## Sheet1
Sprint Number | Task Number | Jira Url | Assignee | Team | Task Title | Task Description | Task start date | Task end date | Status | Priority | Story Point
| M1-261 | https://origat.atlassian.net/browse/M1-261 | Jazzy |  | HKUBS Project - Contact person and communication channel |  | 2025-10-24 |  | Backlog | Medium
| M1-260 | https://origat.atlassian.net/browse/M1-260 | Jazzy |  | Singapore Project - confirm the contact person and communication channel |  | 2025-10-24 |  | Backlog | Medium
| M1-259 | https://origat.atlassian.net/browse/M1-259 | Jazzy |  | Questionnaire that collects info for standardized workflow solution |  | 2025-10-24 |  | Backlog | Medium
| M1-258 | https://origat.atlassian.net/browse/M1-258 | Chung Edmond Tin Ho |  | dev env no data in wp_drawings |  | 2025-10-19 |  | Backlog | Medium
| M1-257 | https://origat.atlassian.net/browse/M1-257 | Chung Edmond Tin Ho |  | 圖紙表修訂版問題 |  | 2025-10-19 |  | Backlog | Medium
| M1-256 | https://origat.atlassian.net/browse/M1-256 | Jazzy |  | M1-02 UIUX UX Pilot Study |  | 2025-10-17 |  | In Progress | Medium
| M1-255 | https://origat.atlassian.net/browse/M1-255 | Jazzy |  | M1-02 UIUX Initial Design |  | 2025-10-17 |  | In Progress | Medium
| M1-254 | https://origat.atlassian.net/browse/M1-254 | Jazzy |  | Shop drawing traditional and M1 Workflow |  | 2025-10-17 |  | In Progress | Medium
| M1-253 | https://origat.atlassian.net/browse/M1-253 |  |  | Project Team User Engagement |  | 2025-10-17 |  | Backlog | Medium
| M1-252 | https://origat.atlassian.net/browse/M1-252 |  |  | Test FTP nodes, currently cant read some Chinese characters (半形中文) |  | 2025-10-17 |  | Backlog | Medium
| M1-251 | https://origat.atlassian.net/browse/M1-251 | Chung Edmond Tin Ho |  | New workflow / webhook for non-drawings |  | 2025-10-17 |  | Backlog | Medium
| M1-250 | https://origat.atlassian.net/browse/M1-250 | Tony Ho |  | Page title space to be shrink Upload section |  | 2025-10-17 |  | Backlog | Medium
| M1-249 | https://origat.atlassian.net/browse/M1-249 |  |  | Files Sometimes Cannot Upload (Bug) |  | 2025-10-17 |  | Backlog | Medium
| M1-248 | https://origat.atlassian.net/browse/M1-248 |  |  | Display Progress of Upload to Public Drive ( Discuss with Tech team) |  | 2025-10-17 |  | Backlog | Medium
| M1-247 | https://origat.atlassian.net/browse/M1-247 |  |  | Fix Bug in Jumping to Page Numbers |  | 2025-10-17 | 2025-10-17 | Done | Medium
| M1-246 | https://origat.atlassian.net/browse/M1-246 |  |  | Departments Permission Controls |  | 2025-10-17 |  | Backlog | Medium
| M1-245 | https://origat.atlassian.net/browse/M1-245 | Chung Edmond Tin Ho |  | review PDF Comparison Function ( Auto feature+ Improvement) |  | 2025-10-17 |  | Backlog | Medium
| M1-244 | https://origat.atlassian.net/browse/M1-244 | Tony Ho |  | Upload: Support Folder Upload Structured by Phase-Discipline-Type |  | 2025-10-17 | 2025-10-19 | Done | Medium
| M1-243 | https://origat.atlassian.net/browse/M1-243 | Tony Ho |  | Allow SZ Department Accounts to Modify Drawing Discipline |  | 2025-10-17 |  | In Progress | Medium
| M1-242 | https://origat.atlassian.net/browse/M1-242 | Tony Ho |  | File Receipt Details Page: Change Sequence to Latest Design Change, Design Change 0 (Initial Data), Design Change 1, etc |  | 2025-10-17 |  | In Progress | Medium
| M1-241 | https://origat.atlassian.net/browse/M1-241 | Tony Ho |  | Upload Page: Add "Drawing Type" and "Design Change Version" Inputs |  | 2025-10-17 | 2025-10-19 | Done | Medium
| M1-240 | https://origat.atlassian.net/browse/M1-240 | Tony Ho |  | Delete the display of time and version in the "Batch Table" |  | 2025-10-17 | 2025-10-19 | Done | Medium
| M1-239 | https://origat.atlassian.net/browse/M1-239 | Jazzy |  | Hide ID Before Each Drawing / Change Upload Page |  | 2025-10-17 | 2025-10-21 | Done | Medium
| M1-238 | https://origat.atlassian.net/browse/M1-238 | Cyrus Chau |  | Bind Corresponding Wechat To M1 |  | 2025-10-17 |  | Backlog | Medium
| M1-237 | https://origat.atlassian.net/browse/M1-237 | Cyrus Chau |  | Bind Corresponding Email To M1 |  | 2025-10-17 |  | Backlog | Medium
| M1-236 | https://origat.atlassian.net/browse/M1-236 | Jazzy |  | Requires confirmation from the Shenzhen department on the notification sending scheme |  | 2025-10-17 |  | In Progress | Medium
| M1-235 | https://origat.atlassian.net/browse/M1-235 | Cyrus Chau |  | "Notify Sender" feature |  | 2025-10-17 |  | In Progress | Medium
| M1-234 | https://origat.atlassian.net/browse/M1-234 |  |  | "Notify Sender" feature |  | 2025-10-17 |  | Backlog | Medium
| M1-233 | https://origat.atlassian.net/browse/M1-233 | Tony Ho |  | Upload Page: Change Sender to "Original Data Source (Company/Person)" |  | 2025-10-17 | 2025-10-19 | Done | Medium
| M1-232 | https://origat.atlassian.net/browse/M1-232 | johnny.ma |  | Reduce Space in Page Title Section |  | 2025-10-17 |  | Backlog | Medium
| M1-231 | https://origat.atlassian.net/browse/M1-231 | Tony Ho |  | Adjust Position of Project Selection, Not in the Middle |  | 2025-10-17 |  | In Progress | Medium
| M1-230 | https://origat.atlassian.net/browse/M1-230 | Tony Ho |  | Save User's Project Level Selection Unless Manually Changed |  | 2025-10-17 |  | In Progress | Medium
| M1-229 | https://origat.atlassian.net/browse/M1-229 |  |  | M1 Refinement Phase 2 (Post UAT) |  | 2025-10-17 |  | Backlog | Medium
| M1-228 | https://origat.atlassian.net/browse/M1-228 | Jazzy |  | Notification Matrix for upload page (notice whom) |  | 2025-10-15 | 2025-10-17 | Done | Medium
| M1-227 | https://origat.atlassian.net/browse/M1-227 | Jazzy |  | M1 refinement- delete upload botton |  | 2025-09-26 | 2025-10-17 | Done | Medium
| M1-226 | https://origat.atlassian.net/browse/M1-226 | Jazzy |  | M1 refinement- number of upload file |  | 2025-09-25 | 2025-10-17 | CLOSED | Medium
| M1-225 | https://origat.atlassian.net/browse/M1-225 | Chung Edmond Tin Ho |  | Internal Demo |  | 2025-09-19 | 2025-09-24 | Backlog | Medium
| M1-224 | https://origat.atlassian.net/browse/M1-224 | Jazzy |  | Review M1-shop drawing spec |  | 2025-09-17 | 2025-09-25 | Done | Medium
| M1-223 | https://origat.atlassian.net/browse/M1-223 | Jazzy |  | M1-refinement |  | 2025-09-17 | 2025-10-17 | CLOSED | Medium
| M1-222 | https://origat.atlassian.net/browse/M1-222 | Jazzy |  | Delete workflow |  | 2025-09-09 | 2025-09-25 | Done | Medium
| M1-221 | https://origat.atlassian.net/browse/M1-221 | Tony Ho |  | Security Issues |  | 2025-09-01 | 2025-09-09 | Done | Medium
| M1-220 | https://origat.atlassian.net/browse/M1-220 |  |  | SZ AliCloud connect to Sundart WebDav |  | 2025-08-29 |  | Backlog | Medium
| M1-219 | https://origat.atlassian.net/browse/M1-219 |  |  | 非圖紙類 Registery |  | 2025-08-29 |  | Backlog | Medium
| M1-218 | https://origat.atlassian.net/browse/M1-218 |  |  | Folder Table |  | 2025-08-29 |  | Backlog | Medium
| M1-217 | https://origat.atlassian.net/browse/M1-217 |  |  | M1-02 Shop Drawing |  | 2025-10-02 | 2025-11-22 | Backlog | Medium
| M1-216 | https://origat.atlassian.net/browse/M1-216 | Jazzy |  | Novade M2 presentation optimization |  | 2025-08-27 | 2025-09-24 | CLOSED | Medium
| M1-215 | https://origat.atlassian.net/browse/M1-215 | Jazzy |  | Coordination of presentation |  | 2025-08-27 | 2025-09-24 | Done | Medium
| M1-214 | https://origat.atlassian.net/browse/M1-214 | Jazzy |  | Talk with Novade employee 28/08 |  | 2025-08-27 | 2025-09-24 | Done | Medium
| M1-213 | https://origat.atlassian.net/browse/M1-213 | Jazzy |  | interview with Tsang about defect process and novade |  | 2025-08-27 | 2025-09-24 | Done | Medium
| M1-212 | https://origat.atlassian.net/browse/M1-212 | Jazzy |  | Shop Drawing Spec Questionnaire |  | 2025-08-26 | 2025-09-24 | Done | Medium
| M1-211 | https://origat.atlassian.net/browse/M1-211 | johnny.ma |  | M1 Stage2 - Shop Drawing Spec |  | 2025-08-26 |  | Backlog | Medium
| M1-210 | https://origat.atlassian.net/browse/M1-210 |  |  | Post-818 User Feedback Implementation |  | 2025-08-25 | 2025-09-29 | In Progress | Medium
| M1-209 | https://origat.atlassian.net/browse/M1-209 | Chung Edmond Tin Ho |  | standalone comparsion WP plugin |  | 2025-08-26 |  | In Progress | Medium
| M1-208 | https://origat.atlassian.net/browse/M1-208 | Chung Edmond Tin Ho |  | python endpoint split_pdf to add directly to ftp and deletes temp files |  | 2025-08-26 |  | In Progress | Medium
| M1-207 | https://origat.atlassian.net/browse/M1-207 | Tony Ho |  | User feedback:上傳的文件在服務器(項目磁盤)找不到，文件夾都無睇到。最新图纸/室内专业/建筑结构图/机电图/图表也不現實内容 |  | 2025-08-26 | 2025-10-19 | Done | Medium
| M1-206 | https://origat.atlassian.net/browse/M1-206 | Chung Edmond Tin Ho |  | RAG (ChatBox) Setup for Drawing Titles and Numbers |  | 2025-08-25 |  | In Progress | Medium
| M1-205 | https://origat.atlassian.net/browse/M1-205 | Tony Ho |  | Bug: Cannot download Batch Zip in "Batch Upload" page | https://61.93.241.82/sdd/?lang=zh-cnBatch Link: https://61.93.241.82/sdd/wp-content/uploads/dms_drawings/2025-08-25-%e9%bb%83%e6%96%b0%e8%88%88%e4%bd%8f%e5%ae%85-batch-12/2025-08-25-%e9%bb%83%e6%96%b0%e8%88%88%e4%bd%8f%e5%ae%85-batch-12.zip | 2025-08-25 | 2025-08-26 | Done | Medium
| M1-204 | https://origat.atlassian.net/browse/M1-204 | Jazzy |  | Novade report and M2 Presentation to sundart top management |  | 2025-08-24 | 2025-09-24 | CLOSED | Medium
| M1-203 | https://origat.atlassian.net/browse/M1-203 | Chung Edmond Tin Ho |  | chatbox to download file from ftp or points to webdav |  | 2025-08-23 |  | In Progress | Medium
| M1-202 | https://origat.atlassian.net/browse/M1-202 | Chung Edmond Tin Ho |  | vector reading mulitple lines |  | 2025-08-23 |  | In Progress | Medium
| M1-201 | https://origat.atlassian.net/browse/M1-201 | Chung Edmond Tin Ho |  | Folder UI Study |  | 2025-08-22 |  | Backlog | Medium
| M1-200 | https://origat.atlassian.net/browse/M1-200 | Cyrus Chau |  | Webdav - Read Only |  | 2025-08-22 |  | Backlog | Medium
| M1-199 | https://origat.atlassian.net/browse/M1-199 | Chung Edmond Tin Ho |  | WP Plug-In |  | 2025-08-22 |  | Backlog | Medium
| M1-198 | https://origat.atlassian.net/browse/M1-198 | Chung Edmond Tin Ho |  | poll from wp_drawings to add to vector db |  | 2025-08-22 |  | In Progress | Medium
| M1-197 | https://origat.atlassian.net/browse/M1-197 | Chung Edmond Tin Ho |  | Web based-Drive |  | 2025-08-22 |  | Backlog | Medium
| M1-196 | https://origat.atlassian.net/browse/M1-196 |  |  | Notification - Whatsapp |  | 2025-08-22 |  | Backlog | Medium
| M1-195 | https://origat.atlassian.net/browse/M1-195 |  |  | Notification - Wechat |  | 2025-08-22 |  | Backlog | Medium
| M1-194 | https://origat.atlassian.net/browse/M1-194 |  |  | Notification User Flow |  | 2025-08-22 |  | Backlog | Medium
| M1-193 | https://origat.atlassian.net/browse/M1-193 |  |  | Notification Function |  | 2025-10-30 | 2025-11-12 | In Progress | Medium
| M1-192 | https://origat.atlassian.net/browse/M1-192 | Chung Edmond Tin Ho |  | 圖差Function review |  | 2025-08-22 |  | In Progress | Medium
| M1-191 | https://origat.atlassian.net/browse/M1-191 |  |  | A Mainland entity to submit ICP for M1 website |  | 2025-08-22 |  | Backlog | Medium
| M1-190 | https://origat.atlassian.net/browse/M1-190 |  |  | SMTP Email server |  | 2025-08-22 |  | Backlog | Medium
| M1-189 | https://origat.atlassian.net/browse/M1-189 | Tony Ho |  | Column name update: add 項目部接收時間 and 項目部上傳時間 |  | 2025-08-22 | 2025-08-22 | Done | Medium
| M1-188 | https://origat.atlassian.net/browse/M1-188 |  |  | Numeric sequencing logic: classify by [Type → Project → Discipline → Discipline running number] |  | 2025-08-22 | 2025-08-22 | CLOSED | Medium
| M1-187 | https://origat.atlassian.net/browse/M1-187 | Tony Ho |  | Bulk Classification |  | 2025-08-22 |  | Backlog | Medium
| M1-186 | https://origat.atlassian.net/browse/M1-186 | Tony Ho |  | CAD Storage user flow (upload / versioning / archiving) |  | 2025-08-22 | 2025-10-19 | Done | Medium
| M1-185 | https://origat.atlassian.net/browse/M1-185 | Tony Ho |  | Add “Other” sub-level under Non-Drawing types |  | 2025-08-22 | 2025-10-19 | Done | Medium
| M1-184 | https://origat.atlassian.net/browse/M1-184 | Tony Ho |  | Add “Other Doc” category under each Discipline |  | 2025-08-22 | 2025-10-19 | Done | Medium
| M1-183 | https://origat.atlassian.net/browse/M1-183 | Cyrus Chau |  | Issue: files re-classified from “Unclassified” not updating to Archive |  | 2025-08-22 |  | Backlog | Medium
| M1-182 | https://origat.atlassian.net/browse/M1-182 | Chung Edmond Tin Ho |  | AI Classification Review (prompt refinement) |  | 2025-08-22 | 2025-08-27 | Backlog | Medium
| M1-181 | https://origat.atlassian.net/browse/M1-181 | Chung Edmond Tin Ho |  | Add Loading Screen |  | 2025-08-22 | 2025-08-25 | CLOSED | Medium
| M1-180 | https://origat.atlassian.net/browse/M1-180 |  |  | Post-818 new request |  | 2025-08-22 | 2025-09-28 | Backlog | Medium
| M1-179 | https://origat.atlassian.net/browse/M1-179 | Cyrus Chau |  | WebDAV Auto Delete Temp Folder Bug Fix |  | 2025-08-19 | 2025-08-20 | Done | Medium
| M1-178 | https://origat.atlassian.net/browse/M1-178 | Cyrus Chau |  | WebDAV Service Email Alert when Task Failed |  | 2025-08-20 | 2025-08-21 | Done | Medium
| M1-177 | https://origat.atlassian.net/browse/M1-177 | Cyrus Chau |  | SMTP Server Setup | TXTaliyundm.dev 48f8e4407e56a27145e7TXTdev v=spf1 include:spfdm-ap-southeast-1.aliyun.com -allTXTaliyun-ap-southeast-1._domainkey.dev v=DKIM1; k=rsa; p=MIGfMA0GCSqGSIb3DQEBAQUAA4GNADCBiQKBgQCjnvrhLc/6vonA4VZPjpxhS5asGBMLf8sweTW9W2uxioaVVF4ggYGKTPEH/7W2nlpg2sgfLg4om/rp566UBVjwo0ywiCCR2PVHWX8OmZwKQCP4YTwZV9sVmTHli3Nb37JDashxTkG12pEgx3wQj0ph2OReuF0lnSwmyEngaRqWIwIDAQABTXT_dmarc.dev v=DMARC1;p=none;rua=mailto:dmarc_report@service.aliyun.comMXdev mxdm-ap-southeast-1.aliyun.com | 2025-08-19 | 2025-08-21 | Done | Medium
| M1-176 | https://origat.atlassian.net/browse/M1-176 |  |  | Issue: FTP WindowsExplorer Folder Name NOT same as File Path | Windows Explorerftp://webdav_sync@61.93.241.82:2121/wp-content/uploads/dms_drawings/2025-08-20-%25e9%25bb%2583%25e6%2596%25b0%25e8%2588%2588%25e4%25bd%258f%25e5%25ae%2585-batch-1/File (Right click Properties)ftp://webdav_sync@61.93.241.82:2121/wp-content/uploads/dms_drawings/2025-08-20-%e9%bb%83%e6%96%b0%e8%88%88%e4%bd%8f%e5%ae%85-batch-1/20221020-AI-MC-034.pdf | 2025-08-20 |  | Backlog | Medium
| M1-175 | https://origat.atlassian.net/browse/M1-175 | Jazzy |  | 磁盘部署 和Team align-----香港部门，深圳部门，工厂部门，项目部公用一个磁盘 |  | 2025-08-19 | 2025-10-17 | Done | Medium
| M1-174 | https://origat.atlassian.net/browse/M1-174 | Jazzy |  | Email Integration （场景确认） |  | 2025-08-19 | 2025-10-17 | Done | Medium
| M1-173 | https://origat.atlassian.net/browse/M1-173 | Jazzy |  | Notification development（场景确认） |  | 2025-08-19 | 2025-09-25 | Done | Medium
| M1-172 | https://origat.atlassian.net/browse/M1-172 | Jazzy |  | Specification Update |  | 2025-08-19 | 2025-08-20 | Done | Medium
| M1-171 | https://origat.atlassian.net/browse/M1-171 | Chung Edmond Tin Ho |  | new endpoint to clean output files (outputs and static) |  | 2025-08-19 |  | In Progress | Medium
| M1-170 | https://origat.atlassian.net/browse/M1-170 | Jazzy |  | 和李经理麻总confirm ROI的数字 |  | 2025-08-18 | 2025-09-25 | Done | Medium
| M1-169 | https://origat.atlassian.net/browse/M1-169 | Jazzy |  | 制作Drawing submission workflow ，align with 李经理和麻总 |  | 2025-08-18 | 2025-09-25 | Done | Medium
| M1-168 | https://origat.atlassian.net/browse/M1-168 | Jazzy |  | 更新“M1产品流程” |  | 2025-08-18 | 2025-08-20 | Done | Medium
| M1-167 | https://origat.atlassian.net/browse/M1-167 | Jazzy |  | 找阿蔡要最新版本的“文件接受明细”，在进行优化 | 1-专业收窄2-每个专业的细分再加上“其他” | 2025-08-18 | 2025-08-24 | Done | Medium
| M1-166 | https://origat.atlassian.net/browse/M1-166 | Tony Ho |  | Bug: Master Sheet -> Batch ID Column -> ID & Folder Path Not Align | How to Reproduce:After coordinator uploaded a new batchDrawing team confirmed new batchGo to master sheet look for the new “Live Design”The latest batch is 43, but in the related Batch ID column shows a different folder pathIn Master Sheet -> Batch ID Column, the ID & Folder Path Not Align. Pls reference attached image.Expected result: ID (Click-able) should be same as Folder Path | 2025-08-16 | 2025-10-19 | CLOSED | Medium
| M1-165 | https://origat.atlassian.net/browse/M1-165 | Tony Ho |  | Bug: Date Receive Issue (Minor, Low-Priority) | The “Date Received” field show another non-related time.How to ReproduceIn Coordinator accountUpload a new batchAfter upload finish, check the “Date Received”There will be Some Chance to show a different older time than expect. | 2025-08-16 |  | Backlog | Medium
| M1-164 | https://origat.atlassian.net/browse/M1-164 |  |  | LLM Api limit study, analyze tokens used on average |  | 2025-08-15 |  | Backlog | Medium
| M1-163 | https://origat.atlassian.net/browse/M1-163 |  |  | Parallel n8n instances workflow study |  | 2025-08-15 |  | Backlog | Medium
| M1-162 | https://origat.atlassian.net/browse/M1-162 |  |  | Modulize n8n functions |  | 2025-08-15 |  | Backlog | Medium
| M1-161 | https://origat.atlassian.net/browse/M1-161 | Cyrus Chau |  | API study - CAD to PDF (Target covert to Vector Data base) |  | 2025-08-15 |  | Backlog | Medium
| M1-160 | https://origat.atlassian.net/browse/M1-160 | Tony Ho |  | create drawing user view |  | 2025-08-14 | 2025-08-25 | Done | Medium
| M1-159 | https://origat.atlassian.net/browse/M1-159 | Tony Ho |  | remove project type selection from coordinator view |  | 2025-08-14 | 2025-08-25 | Done | Medium
| M1-158 | https://origat.atlassian.net/browse/M1-158 | Tony Ho |  | create coordinator account and drawing account |  | 2025-08-14 | 2025-08-25 | Done | Medium
| M1-157 | https://origat.atlassian.net/browse/M1-157 | Tony Ho |  | drawings tables add project display and filter |  | 2025-08-14 | 2025-08-14 | Done | Medium
| M1-156 | https://origat.atlassian.net/browse/M1-156 | Tony Ho |  | mastersheet page add project selection |  | 2025-08-14 | 2025-08-14 | Done | Medium
| M1-155 | https://origat.atlassian.net/browse/M1-155 | Jazzy |  | M1 Specification Draft |  | 2025-08-14 | 2025-08-19 | Done | Medium
| M1-154 | https://origat.atlassian.net/browse/M1-154 |  |  | M1 Specification | Align with user, and present to top-management | 2025-08-14 |  | Backlog | Medium
| M1-153 | https://origat.atlassian.net/browse/M1-153 | Tony Ho |  | add project name selection on batch upload page |  | 2025-08-13 | 2025-08-13 | Done | Medium
| M1-152 | https://origat.atlassian.net/browse/M1-152 | Cyrus Chau |  | File Upload to SZ Queue Service |  | 2025-08-07 | 2025-08-13 | Done | Medium
| M1-151 | https://origat.atlassian.net/browse/M1-151 | Chung Edmond Tin Ho |  | docker sidecar n8n |  | 2025-08-12 | 2025-08-22 | Done | Medium
| M1-150 | https://origat.atlassian.net/browse/M1-150 | Chung Edmond Tin Ho |  | vectors performs better than encoded for LLM study |  | 2025-08-12 |  | In Progress | Medium
| M1-149 | https://origat.atlassian.net/browse/M1-149 | Tony Ho |  | Delete "Drawing Type" in DC Input Page |  | 2025-08-12 | 2025-10-09 | Done | Medium
| M1-148 | https://origat.atlassian.net/browse/M1-148 | moluk |  | Projects Setup |  | 2025-08-12 | 2025-10-09 | Done | Medium
| M1-147 | https://origat.atlassian.net/browse/M1-147 | Tony Ho |  | Tick Function For SZ Team Checking |  | 2025-08-12 | 2025-08-18 | Done | Medium
| M1-146 | https://origat.atlassian.net/browse/M1-146 | Jazzy |  | The workflow diagram traditional and M1 for persentation to top management |  | 2025-08-12 | 2025-08-19 | Done | Medium
| M1-145 | https://origat.atlassian.net/browse/M1-145 | Tony Ho |  | add project name field on batch list display |  | 2025-08-12 | 2025-08-13 | Done | Medium
| M1-144 | https://origat.atlassian.net/browse/M1-144 | Tony Ho |  | latest drawings add confirm button |  | 2025-08-12 | 2025-08-25 | Done | Medium
| M1-143 | https://origat.atlassian.net/browse/M1-143 |  |  | Shop Drawing Submission Schedule - Scope of work and ROI Assessment |  | 2025-08-12 |  | Backlog | Medium
| M1-142 | https://origat.atlassian.net/browse/M1-142 | Jazzy |  | Testing Material Preparation |  | 2025-08-12 | 2025-08-19 | Done | Medium
| M1-141 | https://origat.atlassian.net/browse/M1-141 | Cyrus Chau |  | Test Plan & QA Checklist Doc |  | 2025-08-12 | 2025-08-20 | Done | Medium
| M1-140 | https://origat.atlassian.net/browse/M1-140 | Tony Ho |  | Email Module Integration |  | 2025-10-30 | 2025-11-12 | Backlog | Medium
| M1-139 | https://origat.atlassian.net/browse/M1-139 |  |  | Test Plan & QA Checklist |  | 2025-08-12 | 2025-08-18 | In Progress | Medium
| M1-138 | https://origat.atlassian.net/browse/M1-138 |  |  | Explainer video + Presentation |  | 2025-08-12 | 2025-09-01 | In Progress | Medium
| M1-137 | https://origat.atlassian.net/browse/M1-137 | Cyrus Chau |  | Go To Market - Explainer Video For Presenting M1 |  | 2025-08-11 | 2025-08-25 | In Progress | Medium
| M1-136 | https://origat.atlassian.net/browse/M1-136 | Tony Ho |  | set up accounts and login for otsza01 |  | 2025-08-11 | 2025-08-25 | Done | Medium
| M1-135 | https://origat.atlassian.net/browse/M1-135 | Tony Ho |  | set up alicloud sz instance (call it otsza01) |  | 2025-08-11 | 2025-08-25 | Done | Medium
| M1-134 | https://origat.atlassian.net/browse/M1-134 | Tony Ho |  | Alicloud account KYC |  | 2025-08-11 | 2025-10-17 | Done | Medium
| M1-133 | https://origat.atlassian.net/browse/M1-133 | Tony Ho |  | install other softwares |  | 2025-08-07 | 2025-08-25 | CLOSED | Medium
| M1-132 | https://origat.atlassian.net/browse/M1-132 | Tony Ho |  | install xampp on otsza01 server |  | 2025-08-07 | 2025-08-25 | CLOSED | Medium
| M1-131 | https://origat.atlassian.net/browse/M1-131 | Tony Ho |  | create document for Alicloud server usage |  | 2025-08-07 |  | Backlog | Medium
| M1-130 | https://origat.atlassian.net/browse/M1-130 | Tony Ho |  | set up accounts and login for othka01 server |  | 2025-08-07 | 2025-08-25 | Done | Medium
| M1-129 | https://origat.atlassian.net/browse/M1-129 | Tony Ho |  | install wordpress on otsza01 server |  | 2025-08-07 | 2025-08-25 | Done | Medium
| M1-128 | https://origat.atlassian.net/browse/M1-128 | Tony Ho |  | buy Alicloud server |  | 2025-08-07 | 2025-08-07 | Done | Medium
| M1-127 | https://origat.atlassian.net/browse/M1-127 | Jazzy |  | M2 Defect combined with QS process | 1- 其他专业的问题导致返工 2- 自己没做好导致返工 3-设计变更导致的返工 如果不能完全automatic，可以导出来给项目部人员，手动标签处理 | 2025-08-06 | 2025-08-06 | CLOSED | Medium
| M1-126 | https://origat.atlassian.net/browse/M1-126 | Jazzy |  | 与edmond tony align 文件夹结构，是否可以每个加一个文件夹“原设计”，将pdf有多类图纸的案例放入到里面 |  | 2025-08-04 | 2025-08-20 | Done | Medium
| M1-125 | https://origat.atlassian.net/browse/M1-125 | Jazzy |  | 根据李经理，阿蔡align的内容，制作流程图 | 现场dc根据专业将图纸资料放入M1中，系统自动生成drawing registry以及自动归档，其中drawing registry中，drawing title和文件位置放在一起，李经理可以crosscheck | 2025-08-04 | 2025-08-20 | Done | Medium
| M1-124 | https://origat.atlassian.net/browse/M1-124 | Chung Edmond Tin Ho |  | Analyse Sundart Testing Email Attachment |  | 2025-08-04 |  | Backlog | Medium
| M1-123 | https://origat.atlassian.net/browse/M1-123 | Chung Edmond Tin Ho |  | pdf file handling issues (over 1500 pages) |  | 2025-08-04 | 2025-08-12 | CLOSED | Medium
| M1-122 | https://origat.atlassian.net/browse/M1-122 |  |  | Separate ai and maual data |  | 2025-08-01 |  | Backlog | Medium
| M1-121 | https://origat.atlassian.net/browse/M1-121 | Chung Edmond Tin Ho |  | add WebDav function to python |  | 2025-08-12 | 2025-08-16 | Done | Medium
| M1-120 | https://origat.atlassian.net/browse/M1-120 | Tony Ho |  | master sheet layout change |  | 2025-07-31 | 2025-08-07 | Done | Medium
| M1-119 | https://origat.atlassian.net/browse/M1-119 | Tony Ho |  | batch upload page layout change |  | 2025-07-31 | 2025-08-07 | Done | Medium
| M1-118 | https://origat.atlassian.net/browse/M1-118 | Cyrus Chau |  | Blue beam 数据库/是否有手机版本 |  | 2025-07-30 |  | Backlog | Medium
| M1-117 | https://origat.atlassian.net/browse/M1-117 | Jazzy |  | Email Attachment Tagging Table (分類Hierarchy) |  | 2025-07-30 | 2025-07-30 | Done | Medium
| M1-116 | https://origat.atlassian.net/browse/M1-116 | Chung Edmond Tin Ho |  | RAG Setup for all drawing and docs |  | 2025-07-30 | 2025-08-18 | Done | Medium
| M1-115 | https://origat.atlassian.net/browse/M1-115 | Chung Edmond Tin Ho |  | mysql db restructure |  | 2025-07-29 | 2025-07-31 | Done | Medium
| M1-114 | https://origat.atlassian.net/browse/M1-114 | Chung Edmond Tin Ho |  | Drawing Label Web Frontend |  | 2025-07-29 | 2025-08-22 | Done | Medium
| M1-113 | https://origat.atlassian.net/browse/M1-113 |  |  | Drawing Label |  | 2025-07-15 | 2025-08-18 | Backlog | Medium
| M1-112 | https://origat.atlassian.net/browse/M1-112 | Tony Ho |  | Drawing Label - Issue Status & Type |  | 2025-07-29 | 2025-10-19 | CLOSED | Medium
| M1-111 | https://origat.atlassian.net/browse/M1-111 | Jazzy |  | Collect user requirement from SZ 畫圖部 |  | 2025-07-29 | 2025-08-11 | Done | Medium
| M1-110 | https://origat.atlassian.net/browse/M1-110 | Chung Edmond Tin Ho |  | Chatbox - feasibility study |  | 2025-07-29 | 2025-10-09 | Done | Medium
| M1-109 | https://origat.atlassian.net/browse/M1-109 | Jazzy |  | Shop Drawing Submission Schedule Workflow |  | 2025-07-15 | 2025-07-31 | Done | Medium
| M1-108 | https://origat.atlassian.net/browse/M1-108 | Cyrus Chau |  | 2.5 深圳網盤整合 |  | 2025-07-29 | 2025-08-01 | Done | Medium
| M1-107 | https://origat.atlassian.net/browse/M1-107 | Jazzy |  | Quarterly Meeting Meeting minute and key points |  | 2025-07-28 | 2025-07-30 | Done | Medium
| M1-105 | https://origat.atlassian.net/browse/M1-105 | Chung Edmond Tin Ho |  | Standalone php file |  | 2025-07-28 | 2025-07-31 | Done | Medium
| M1-104 | https://origat.atlassian.net/browse/M1-104 | Jazzy |  | 功能 1 協調並確認 ROI 評估方向（與 Domain Expert 對齊） |  | 2025-07-29 | 2025-07-30 | Done | Medium
| M1-103 | https://origat.atlassian.net/browse/M1-103 | Jazzy |  | 功能 2 (Phase 2) 協調並確認 ROI 評估方向（與 Domain Expert 對齊） |  | 2025-07-29 | 2025-07-30 | Done | Medium
| M1-102 | https://origat.atlassian.net/browse/M1-102 | Jazzy |  | 3.1 (Phase 1) 協調並確認 ROI 評估方向（與 Domain Expert 對齊） |  | 2025-07-29 | 2025-07-30 | Done | Medium
| M1-101 | https://origat.atlassian.net/browse/M1-101 |  |  | https://origat.atlassian.net/jira/software/projects/ORIGA/list?filter=updated%20%3E%3D%202025-07-18 功能1 ROI評估ALIGNMENT WI |  | 2025-07-25 |  | Backlog | Medium
| M1-100 | https://origat.atlassian.net/browse/M1-100 | Jazzy |  | Alignment with domain expert about ROI template | 我们希望得到的ROI评估维度为：时间节省：如：单次任务人工录入时间从20分钟降至5分钟人力成本节省：如：初级工程师时薪 × 节省时间 × 月频次风险降低：如：数据错误率从30%降至5%业务影响：如：加速项目审批，减少返工 但是Domain给到的仅有时间维度，且功能4-11没有给出discovery protocol阶段的预估ROI | 2025-07-28 | 2025-07-30 | Done | Medium
| M1-99 | https://origat.atlassian.net/browse/M1-99 | Jazzy |  | Quarterly meeting presentation ppt | Present clearly M2 | 2025-07-25 | 2025-07-26 | Done | Medium
| M1-98 | https://origat.atlassian.net/browse/M1-98 | Jazzy |  | AI Strategy Feasibility Study |  | 2025-07-21 | 2025-07-27 | Done | Medium
| M1-97 | https://origat.atlassian.net/browse/M1-97 | Tony Ho |  | research peft |  | 2025-07-25 |  | Backlog | Medium
| M1-96 | https://origat.atlassian.net/browse/M1-96 |  |  | Production Environment |  | 2025-07-15 | 2025-09-17 | Backlog | Medium
| M1-95 | https://origat.atlassian.net/browse/M1-95 | Jazzy |  | 問user拎網盤list |  | 2025-07-29 | 2025-07-30 | Done | Medium
| M1-94 | https://origat.atlassian.net/browse/M1-94 | Jazzy |  | 問user拎業務電郵例子 |  | 2025-07-29 | 2025-08-11 | Done | Medium
| M1-93 | https://origat.atlassian.net/browse/M1-93 | Tony Ho |  | deploy product function 3 onto production |  | 2025-08-11 | 2025-08-18 | Done | Medium
| M1-92 | https://origat.atlassian.net/browse/M1-92 | Tony Ho |  | deploy product function 2 onto production |  | 2025-07-25 | 2025-10-09 | Done | Medium
| M1-91 | https://origat.atlassian.net/browse/M1-91 | Tony Ho |  | deploy product function 1 onto production |  | 2025-07-25 | 2025-10-09 | Done | Medium
| M1-90 | https://origat.atlassian.net/browse/M1-90 | Tony Ho |  | set up production environment |  | 2025-07-25 | 2025-10-17 | Done | Medium
| M1-89 | https://origat.atlassian.net/browse/M1-89 | Tony Ho |  | Contact alicloud for solutions and quotes |  | 2025-07-25 | 2025-08-11 | Done | Medium
| M1-88 | https://origat.atlassian.net/browse/M1-88 | Tony Ho |  | onedrive (Closed) |  | 2025-07-24 | 2025-08-04 | CLOSED | Medium
| M1-87 | https://origat.atlassian.net/browse/M1-87 | Tony Ho |  | dropbox |  | 2025-07-24 |  | Backlog | Medium
| M1-86 | https://origat.atlassian.net/browse/M1-86 | Tony Ho |  | google drive |  | 2025-07-24 |  | Backlog | Medium
| M1-85 | https://origat.atlassian.net/browse/M1-85 | Tony Ho |  | 百度網盤 |  | 2025-07-24 |  | Backlog | Medium
| M1-83 | https://origat.atlassian.net/browse/M1-83 | Tony Ho |  | multi language |  | 2025-07-23 | 2025-07-24 | Done | Medium
| M1-82 | https://origat.atlassian.net/browse/M1-82 | Jazzy |  | 功能 11 手稿掃描圖處理 |  | 2025-07-15 | 2025-07-29 | CLOSED | Medium
| M1-81 | https://origat.atlassian.net/browse/M1-81 | Jazzy |  | 功能 10 無圖框圖紙處理 |  | 2025-07-15 | 2025-07-29 | CLOSED | Medium
| M1-80 | https://origat.atlassian.net/browse/M1-80 | Jazzy |  | 功能 9 潔具五金 doc 處理 |  | 2025-07-15 | 2025-07-29 | CLOSED | Medium
| M1-79 | https://origat.atlassian.net/browse/M1-79 | Cyrus Chau |  | 功能 8 CAD 圖差識別 |  | 2025-07-15 | 2025-07-29 | CLOSED | Medium
| M1-78 | https://origat.atlassian.net/browse/M1-78 | Cyrus Chau |  | 功能 7 CAD 自動歸檔 |  | 2025-07-15 | 2025-07-29 | In Progress | Medium
| M1-77 | https://origat.atlassian.net/browse/M1-77 | Cyrus Chau |  | 功能 6 CAD 圖檔 intake |  | 2025-07-15 | 2025-07-29 | In Progress | Medium
| M1-76 | https://origat.atlassian.net/browse/M1-76 | Jazzy |  | 功能 5 shop drawing 排程 |  | 2025-07-22 | 2025-07-30 | CLOSED | Medium
| M1-75 | https://origat.atlassian.net/browse/M1-75 | Chung Edmond Tin Ho |  | 功能 4 AI 文件調取助手 (RAG) |  | 2025-07-22 | 2025-09-07 | Backlog | Medium
| M1-74 | https://origat.atlassian.net/browse/M1-74 | Chung Edmond Tin Ho |  | 3.2 圖差識別演算法優化 (Phase 2) |  | 2025-08-19 | 2025-08-25 | In Progress | Medium
| M1-73 | https://origat.atlassian.net/browse/M1-73 | Chung Edmond Tin Ho |  | 3.1 圖差識別 (Phase 1) |  | 2025-07-30 | 2025-08-10 | Done | Medium
| M1-72 | https://origat.atlassian.net/browse/M1-72 |  |  | 功能 3 圖差識別 |  | 2025-07-16 | 2025-08-18 | Backlog | Medium
| M1-71 | https://origat.atlassian.net/browse/M1-71 |  |  | 2.7 個人化 Folder 結構 (AI Chatbox) |  | 2025-07-22 | 2025-07-30 | Done | Medium
| M1-70 | https://origat.atlassian.net/browse/M1-70 | Cyrus Chau |  | 2.5 MyQNAPCloud API 深圳網盤研究 |  | 2025-07-18 | 2025-07-25 | Done | Medium
| M1-69 | https://origat.atlassian.net/browse/M1-69 | Tony Ho |  | 2.4 各類網盤登入與下載 |  | 2025-07-16 | 2025-08-18 | Backlog | Medium
| M1-68 | https://origat.atlassian.net/browse/M1-68 | Tony Ho |  | 2.3 Email 處理模組 |  | 2025-05-02 | 2025-08-18 | Backlog | Medium
| M1-67 | https://origat.atlassian.net/browse/M1-67 | Chung Edmond Tin Ho |  | 2.2 圖紙自動歸檔 (Folder-based) |  | 2025-07-16 | 2025-08-18 | Done | Medium
| M1-66 | https://origat.atlassian.net/browse/M1-66 | Chung Edmond Tin Ho |  | 2.1 圖紙自動歸檔 (Web-based) | 不包含 Email metadata | 2025-07-25 | 2025-08-11 | CLOSED | Medium
| M1-65 | https://origat.atlassian.net/browse/M1-65 | Chung Edmond Tin Ho |  | 2.6 Folder rule-based 結構整理 | 使用rule-based / AI-based歸檔邏輯（email / wechat） | 2025-07-18 | 2025-08-04 | CLOSED | Medium
| M1-64 | https://origat.atlassian.net/browse/M1-64 |  |  | 功能 2 (Phase 2) 圖紙⾃動歸檔 |  | 2025-07-25 | 2025-08-18 | Backlog | Medium
| M1-63 | https://origat.atlassian.net/browse/M1-63 | Jazzy |  | Discipline 規則整理 | 幫助task 2.3.1定義rule-based邏輯 | 2025-07-18 | 2025-07-29 | Done | Medium
| M1-62 | https://origat.atlassian.net/browse/M1-62 | Chung Edmond Tin Ho |  | Discipline 類型資料庫擴充 | 加入 MEP-Mapping 至 CSD 類型，修改 DB 結構 | 2025-07-18 | 2025-08-04 | CLOSED | Medium
| M1-61 | https://origat.atlassian.net/browse/M1-61 | Tony Ho |  | 多語言顯示介面 | 支援繁體 / 簡體 / 英文介面 | 2025-07-18 | 2025-07-31 | Done | Medium
| M1-60 | https://origat.atlassian.net/browse/M1-60 |  |  | 功能 1 圖紙接受明細 |  | 2025-07-18 | 2025-08-18 | In Progress | Medium
| M1-59 | https://origat.atlassian.net/browse/M1-59 | johnny.ma |  | GoogleDrive integration |  | 2025-07-15 |  | Backlog | Medium
| M1-58 | https://origat.atlassian.net/browse/M1-58 | johnny.ma |  | 阿里雲網盤 integration |  | 2025-07-15 |  | Backlog | Medium
| M1-57 | https://origat.atlassian.net/browse/M1-57 | johnny.ma |  | 百度網盤 integration |  | 2025-07-15 |  | Backlog | Medium
| M1-56 | https://origat.atlassian.net/browse/M1-56 | johnny.ma |  | Take a look at the Testing Mailbox from 蔡小姐 |  | 2025-07-15 |  | Backlog | Medium
| M1-55 | https://origat.atlassian.net/browse/M1-55 | johnny.ma |  | URL Link auto detect in email |  | 2025-07-15 |  | Backlog | Medium
| M1-54 | https://origat.atlassian.net/browse/M1-54 | johnny.ma |  | CAD attachment folder & category |  | 2025-07-15 |  | Backlog | Medium
| M1-53 | https://origat.atlassian.net/browse/M1-53 | johnny.ma |  | Email unread after data fetched |  | 2025-07-15 |  | Backlog | Medium
| M1-52 | https://origat.atlassian.net/browse/M1-52 | johnny.ma |  | pdf fills database |  | 2025-06-26 | 2025-07-09 | Backlog | Medium
| M1-51 | https://origat.atlassian.net/browse/M1-51 | Chung Edmond Tin Ho |  | Design model architecture, define data requirements |  | 2025-07-04 | 2025-07-30 | Done | Medium
| M1-50 | https://origat.atlassian.net/browse/M1-50 | Jazzy |  | Collect workflow data, draft as-is flow, map AI touchpoints |  | 2025-07-14 | 2025-07-13 | Done | Medium
| M1-49 | https://origat.atlassian.net/browse/M1-49 | johnny.ma |  | RAG + MCP Direction Study |  | 2025-07-04 | 2025-07-15 | Done | Medium
| M1-48 | https://origat.atlassian.net/browse/M1-48 | johnny.ma |  | AI Classifier (ML doc type classification) |  | 2025-07-04 | 2025-07-15 | Done | Medium
| M1-47 | https://origat.atlassian.net/browse/M1-47 | johnny.ma |  | OrigaT Agent M1 Preparation (Next: Shop Drawing Flow) |  | 2025-07-04 | 2025-07-25 | Done | Medium
| M1-46 | https://origat.atlassian.net/browse/M1-46 | Jazzy |  | 優劣勢總結與產品策略建議 | 總結萬翼相對於我們現有方案的優勢、短板、風險，提出初步產品策略建議 | 2025-07-04 | 2025-07-09 | Done | Medium
| M1-45 | https://origat.atlassian.net/browse/M1-45 | Jazzy |  | 潛在引入或合作可行性分析 | 評估萬翼方案的技術或模組是否適合引入 Origa Agent M1，以及合作可行性和風險 | 2025-07-04 | 2025-07-09 | Done | Medium
| M1-44 | https://origat.atlassian.net/browse/M1-44 | Jazzy |  | 市場定位與商業模式調研 |  | 2025-07-04 | 2025-07-09 | Done | Medium
| M1-43 | https://origat.atlassian.net/browse/M1-43 | Jazzy |  | 技術架構與實現方式分析 | 研究萬翼的技術方案（圖框識別、CAD 矢量處理、BIM 輕量化、數據留痕等），評估可借鑑之處。 | 2025-07-04 | 2025-07-09 | Done | Medium
| M1-42 | https://origat.atlassian.net/browse/M1-42 | Jazzy |  | 功能完整度分析 | 評估萬翼 AI 圖雲在圖紙管理、審查、批註、問題追蹤、版本對比、現場應用等功能的完整性和成熟度。 | 2025-07-04 | 2025-07-09 | Done | Medium
| M1-41 | https://origat.atlassian.net/browse/M1-41 | johnny.ma |  | In-depth Study of萬翼 AI 圖雲 Solution |  | 2025-07-07 | 2025-07-11 | Done | Medium
| M1-40 | https://origat.atlassian.net/browse/M1-40 | johnny.ma |  | two layers to consider catergory and types for trash bin |  | 2025-06-27 | 2025-07-09 | Backlog | Medium
| M1-38 | https://origat.atlassian.net/browse/M1-38 | johnny.ma |  | expect pdf to be all the same discipline |  | 2025-06-27 | 2025-07-09 | Backlog | Medium
| M1-37 | https://origat.atlassian.net/browse/M1-37 | Chung Edmond Tin Ho |  | meta vertify |  | 2025-06-26 | 2025-06-26 | Done | Medium
| M1-36 | https://origat.atlassian.net/browse/M1-36 | johnny.ma |  | video editing / VR idea |  | 2025-06-26 |  | Backlog | Medium
| M1-34 | https://origat.atlassian.net/browse/M1-34 | johnny.ma |  | add a page to trash bin, its a list, then drawing name for the pdf, then able to select discipline and marked sent |  | 2025-06-25 | 2025-07-09 | Backlog | Medium
| M1-33 | https://origat.atlassian.net/browse/M1-33 | Chung Edmond Tin Ho |  | pending domain expert input 100-500 pdf |  | 2025-06-24 | 2025-07-09 | CLOSED | Medium
| M1-32 | https://origat.atlassian.net/browse/M1-32 | Jazzy |  | Funcntion 3 user requirements exploration UIUX |  | 2025-06-24 | 2025-07-09 | Done | Medium
| M1-31 | https://origat.atlassian.net/browse/M1-31 | johnny.ma |  | Lark discussion with mo |  | 2025-06-24 | 2025-07-09 | Backlog | Medium
| M1-30 | https://origat.atlassian.net/browse/M1-30 | Chung Edmond Tin Ho |  | FTP saves splitted pdf |  | 2025-06-27 | 2025-06-28 | Done | Medium
| M1-27 | https://origat.atlassian.net/browse/M1-27 | Chung Edmond Tin Ho |  | changes datas |  | 2025-06-24 | 2025-07-09 | Done | Medium
| M1-26 | https://origat.atlassian.net/browse/M1-26 | Chung Edmond Tin Ho |  | Main Spreadsheet |  | 2025-06-24 | 2025-07-09 | Done | Medium
| M1-25 | https://origat.atlassian.net/browse/M1-25 | Chung Edmond Tin Ho |  | Configure n8n, python mysql and wordpress |  | 2025-06-25 | 2025-06-27 | Done | Medium
| M1-24 | https://origat.atlassian.net/browse/M1-24 | Chung Edmond Tin Ho |  | Learn keywords from sorting bin |  | 2025-06-24 | 2025-07-09 | CLOSED | Medium
| M1-23 | https://origat.atlassian.net/browse/M1-23 | Chung Edmond Tin Ho |  | Bin PDF Function |  | 2025-06-24 | 2025-07-09 | CLOSED | Medium
| M1-22 | https://origat.atlassian.net/browse/M1-22 | Chung Edmond Tin Ho |  | mysql id to ftp file |  | 2025-06-26 | 2025-06-29 | Done | Medium
| M1-15 | https://origat.atlassian.net/browse/M1-15 | johnny.ma |  | OrigaT Agent M1 (15/7 MVP) |  | 2025-06-22 | 2025-07-11 | Done | Medium
| M1-14 | https://origat.atlassian.net/browse/M1-14 | Jazzy |  | Organize the implementation details of Agent M1 and create a clear process flowchart. |  | 2025-06-13 | 2025-06-20 | Done | Medium
| M1-13 | https://origat.atlassian.net/browse/M1-13 | Jazzy |  | Based on the interviews, organize the details of the drawing distribution process, including the content to be distributed, etc. |  | 2025-06-13 | 2025-06-20 | Done | Medium
| M1-12 | https://origat.atlassian.net/browse/M1-12 | Jazzy |  | Interview with Felix, relize traditional project drawing related process |  | 2025-06-13 | 2025-06-20 | Done | Medium
| M1-11 | https://origat.atlassian.net/browse/M1-11 | johnny.ma |  | Product requirement discussion with Domain Expert in SZ office |  | 2025-05-22 | 2025-05-22 | Done | Medium
| M1-10 | https://origat.atlassian.net/browse/M1-10 | johnny.ma |  | n8n framework feasibility study completed |  | 2025-05-22 | 2025-05-22 | Done | Medium
| M1-9 | https://origat.atlassian.net/browse/M1-9 | johnny.ma |  | Kick-off meeting with Patrick and Isaac |  | 2025-05-22 | 2025-05-22 | Done | Medium
| M1-8 | https://origat.atlassian.net/browse/M1-8 | johnny.ma |  | Presentation Prep: Demo to 麻總 & 李經理 | Prepare slides, sample data, and live flow demo for the Week 1 June presentation; schedule meeting and send invites. | 2025-05-22 | 2025-06-02 | Done | Medium
| M1-7 | https://origat.atlassian.net/browse/M1-7 | Jazzy |  | Detailed Project Plan Document | Create “Origa Agent M1 Detailed Project Plan” using the agreed outline (Cover, Intro, Definition, Business Case, Plan, Control, Appendix). | 2025-05-22 | 2025-05-31 | Done | Medium
| M1-6 | https://origat.atlassian.net/browse/M1-6 | Jazzy |  | Prompt Engineering for PDF Extraction | Review the PDF-extraction workflow with Edmond; identify all nodes needing prompts; draft and document exact prompt text for each node. | 2025-05-22 | 2025-05-31 | Done | Medium
| M1-5 | https://origat.atlassian.net/browse/M1-5 | Chung Edmond Tin Ho |  | Function 4: SMS Notification Integration | Define SMS-notification use cases, select provider (e.g., Twilio), and configure n8n node(s) to send alerts at key checkpoints. | 2025-05-22 | 2025-05-31 | Done | Medium
| M1-4 | https://origat.atlassian.net/browse/M1-4 | Chung Edmond Tin Ho |  | Function 3: Project-based Archive Structure | Extend the auto-save flow to implement any remaining archive logic for project folders and subfolders, as per spec. | 2025-05-22 | 2025-05-31 | Done | Medium
| M1-3 | https://origat.atlassian.net/browse/M1-3 | Chung Edmond Tin Ho |  | Function 2: Auto-save by Project | Build n8n workflow to auto-save files into the domain-expert-defined folder structure, organized per project. Verify naming conventions and folder creation logic. | 2025-05-22 | 2025-05-23 | Done | Medium
| M1-2 | https://origat.atlassian.net/browse/M1-2 | Chung Edmond Tin Ho |  | Function 1: Drawing Register Table | Implement “Drawing Register” n8n workflow: collect incoming attachments, extract metadata, and populate the drawing-reception checklist table. | 2025-05-22 | 2025-05-20 | Done | Medium
| M1-1 | https://origat.atlassian.net/browse/M1-1 | johnny.ma |  | First Product Demo (May) |  | 2025-05-22 | 2025-06-02 | Done | Medium