## Tasks
Sprint Number | Task Number | Assignee | Team | Task Title | Task Description | Task start date | Task end date | Status | Priority | Story Point
| M1-258 | Chung Edmond Tin Ho |  | dev env no data in wp_drawings |  | 2025-10-19 |  | Backlog | Medium
| M1-257 | Chung Edmond Tin Ho |  | 圖紙表修訂版問題 |  | 2025-10-19 |  | Backlog | Medium
| M1-256 | Jazzy |  | M1-02 UIUX UX Pilot Study |  | 2025-10-17 |  | In Progress | Medium
| M1-255 | Jazzy |  | M1-02 UIUX Initial Design |  | 2025-10-17 |  | In Progress | Medium
| M1-254 | Jazzy |  | Shop drawing traditional and M1 Workflow |  | 2025-10-17 |  | In Progress | Medium
| M1-253 |  |  | Project Team User Engagement |  | 2025-10-17 |  | Backlog | Medium
| M1-252 |  |  | Test FTP nodes, currently cant read some Chinese characters (半形中文) |  | 2025-10-17 |  | Backlog | Medium
| M1-251 | Chung Edmond Tin Ho |  | New workflow / webhook for non-drawings |  | 2025-10-17 |  | Backlog | Medium
| M1-250 | Tony Ho |  | Page title space to be shrink Upload section |  | 2025-10-17 |  | Backlog | Medium
| M1-249 |  |  | Files Sometimes Cannot Upload (Bug) |  | 2025-10-17 |  | Backlog | Medium
| M1-248 |  |  | Display Progress of Upload to Public Drive ( Discuss with Tech team) |  | 2025-10-17 |  | Backlog | Medium
| M1-247 |  |  | Fix Bug in Jumping to Page Numbers |  | 2025-10-17 | 2025-10-17 | Done | Medium
| M1-246 |  |  | Departments Permission Controls |  | 2025-10-17 |  | Backlog | Medium
| M1-245 | Chung Edmond Tin Ho |  | review PDF Comparison Function ( Auto feature+ Improvement) |  | 2025-10-17 |  | Backlog | Medium
| M1-244 | Tony Ho |  | Upload: Support Folder Upload Structured by Phase-Discipline-Type |  | 2025-10-17 | 2025-10-19 | Done | Medium
| M1-243 | Tony Ho |  | Allow SZ Department Accounts to Modify Drawing Discipline |  | 2025-10-17 |  | In Progress | Medium
| M1-242 | Tony Ho |  | File Receipt Details Page: Change Sequence to Latest Design Change, Design Change 0 (Initial Data), Design Change 1, etc |  | 2025-10-17 |  | In Progress | Medium
| M1-241 | Tony Ho |  | Upload Page: Add "Drawing Type" and "Design Change Version" Inputs |  | 2025-10-17 | 2025-10-19 | Done | Medium
| M1-240 | Tony Ho |  | Delete the display of time and version in the "Batch Table" |  | 2025-10-17 | 2025-10-19 | Done | Medium
| M1-239 | Jazzy |  | Hide ID Before Each Drawing / Change Upload Page |  | 2025-10-17 | 2025-10-21 | Done | Medium
| M1-238 | Cyrus Chau |  | Bind Corresponding Wechat To M1 |  | 2025-10-17 |  | Backlog | Medium
| M1-237 | Cyrus Chau |  | Bind Corresponding Email To M1 |  | 2025-10-17 |  | Backlog | Medium
| M1-236 | Jazzy |  | Requires confirmation from the Shenzhen department on the notification sending scheme |  | 2025-10-17 |  | In Progress | Medium
| M1-235 | Cyrus Chau |  | "Notify Sender" feature |  | 2025-10-17 |  | In Progress | Medium
| M1-234 |  |  | "Notify Sender" feature |  | 2025-10-17 |  | Backlog | Medium
| M1-233 | Tony Ho |  | Upload Page: Change Sender to "Original Data Source (Company/Person)" |  | 2025-10-17 | 2025-10-19 | Done | Medium
| M1-232 | johnny.ma |  | Reduce Space in Page Title Section |  | 2025-10-17 |  | Backlog | Medium
| M1-231 | Tony Ho |  | Adjust Position of Project Selection, Not in the Middle |  | 2025-10-17 |  | In Progress | Medium
| M1-230 | Tony Ho |  | Save User's Project Level Selection Unless Manually Changed |  | 2025-10-17 |  | In Progress | Medium
| M1-229 |  |  | M1 Refinement Phase 2 (Post UAT) |  | 2025-10-17 |  | Backlog | Medium
| M1-228 | Jazzy |  | Notification Matrix for upload page (notice whom) |  | 2025-10-15 | 2025-10-17 | Done | Medium
| M1-227 | Jazzy |  | M1 refinement- delete upload botton |  | 2025-09-26 | 2025-10-17 | Done | Medium
| M1-226 | Jazzy |  | M1 refinement- number of upload file |  | 2025-09-25 | 2025-10-17 | CLOSED | Medium
| M1-225 |  |  | Internal Demo |  | 2025-09-19 | 2025-09-24 | Backlog | Medium
| M1-224 | Jazzy |  | Review M1-shop drawing spec |  | 2025-09-17 | 2025-09-25 | Done | Medium
| M1-223 | Jazzy |  | M1-refinement |  | 2025-09-17 | 2025-10-17 | CLOSED | Medium
| M1-222 | Jazzy |  | Delete workflow |  | 2025-09-09 | 2025-09-25 | Done | Medium
| M1-221 | Tony Ho |  | Security Issues |  | 2025-09-01 | 2025-09-09 | Done | Medium
| M1-220 |  |  | SZ AliCloud connect to Sundart WebDav |  | 2025-08-29 |  | Backlog | Medium
| M1-219 |  |  | 非圖紙類 Registery |  | 2025-08-29 |  | Backlog | Medium
| M1-218 |  |  | Folder Table |  | 2025-08-29 |  | Backlog | Medium
| M1-217 |  |  | M1-02 Shop Drawing |  | 2025-10-02 | 2025-11-22 | Backlog | Medium
| M1-216 | Jazzy |  | Novade M2 presentation optimization |  | 2025-08-27 | 2025-09-24 | CLOSED | Medium
| M1-215 | Jazzy |  | Coordination of presentation |  | 2025-08-27 | 2025-09-24 | Done | Medium
| M1-214 | Jazzy |  | Talk with Novade employee 28/08 |  | 2025-08-27 | 2025-09-24 | Done | Medium
| M1-213 | Jazzy |  | interview with Tsang about defect process and novade |  | 2025-08-27 | 2025-09-24 | Done | Medium
| M1-212 | Jazzy |  | Shop Drawing Spec Questionnaire |  | 2025-08-26 | 2025-09-24 | Done | Medium
| M1-211 | johnny.ma |  | M1 Stage2 - Shop Drawing Spec |  | 2025-08-26 |  | Backlog | Medium
| M1-210 |  |  | Post-818 User Feedback Implementation |  | 2025-08-25 | 2025-09-29 | In Progress | Medium
| M1-209 | Chung Edmond Tin Ho |  | standalone comparsion WP plugin |  | 2025-08-26 |  | In Progress | Medium
| M1-208 | Chung Edmond Tin Ho |  | python endpoint split_pdf to add directly to ftp and deletes temp files |  | 2025-08-26 |  | In Progress | Medium
| M1-207 | Tony Ho |  | User feedback:上傳的文件在服務器(項目磁盤)找不到，文件夾都無睇到。最新图纸/室内专业/建筑结构图/机电图/图表也不現實内容 |  | 2025-08-26 | 2025-10-19 | Done | Medium
| M1-206 | Chung Edmond Tin Ho |  | RAG (ChatBox) Setup for Drawing Titles and Numbers |  | 2025-08-25 |  | In Progress | Medium
| M1-205 | Tony Ho |  | Bug: Cannot download Batch Zip in "Batch Upload" page | https://61.93.241.82/sdd/?lang=zh-cnBatch Link: https://61.93.241.82/sdd/wp-content/uploads/dms_drawings/2025-08-25-%e9%bb%83%e6%96%b0%e8%88%88%e4%bd%8f%e5%ae%85-batch-12/2025-08-25-%e9%bb%83%e6%96%b0%e8%88%88%e4%bd%8f%e5%ae%85-batch-12.zip | 2025-08-25 | 2025-08-26 | Done | Medium
| M1-204 | Jazzy |  | Novade report and M2 Presentation to sundart top management |  | 2025-08-24 | 2025-09-24 | CLOSED | Medium
| M1-203 | Chung Edmond Tin Ho |  | chatbox to download file from ftp or points to webdav |  | 2025-08-23 |  | In Progress | Medium
| M1-202 | Chung Edmond Tin Ho |  | vector reading mulitple lines |  | 2025-08-23 |  | In Progress | Medium
| M1-201 | Chung Edmond Tin Ho |  | Folder UI Study |  | 2025-08-22 |  | Backlog | Medium
| M1-200 | Cyrus Chau |  | Webdav - Read Only |  | 2025-08-22 |  | Backlog | Medium
| M1-199 | Chung Edmond Tin Ho |  | WP Plug-In |  | 2025-08-22 |  | Backlog | Medium
| M1-198 | Chung Edmond Tin Ho |  | poll from wp_drawings to add to vector db |  | 2025-08-22 |  | In Progress | Medium
| M1-197 | Chung Edmond Tin Ho |  | Web based-Drive |  | 2025-08-22 |  | Backlog | Medium
| M1-196 |  |  | Notification - Whatsapp |  | 2025-08-22 |  | Backlog | Medium
| M1-195 |  |  | Notification - Wechat |  | 2025-08-22 |  | Backlog | Medium
| M1-194 |  |  | Notification User Flow |  | 2025-08-22 |  | Backlog | Medium
| M1-193 |  |  | Notification Function |  | 2025-10-30 | 2025-11-12 | In Progress | Medium
| M1-192 | Chung Edmond Tin Ho |  | 圖差Function review |  | 2025-08-22 |  | In Progress | Medium
| M1-191 |  |  | A Mainland entity to submit ICP for M1 website |  | 2025-08-22 |  | Backlog | Medium
| M1-190 |  |  | SMTP Email server |  | 2025-08-22 |  | Backlog | Medium
| M1-189 | Tony Ho |  | Column name update: add 項目部接收時間 and 項目部上傳時間 |  | 2025-08-22 | 2025-08-22 | Done | Medium
| M1-188 |  |  | Numeric sequencing logic: classify by [Type → Project → Discipline → Discipline running number] |  | 2025-08-22 | 2025-08-22 | CLOSED | Medium
| M1-187 | Tony Ho |  | Bulk Classification |  | 2025-08-22 |  | Backlog | Medium
| M1-186 | Tony Ho |  | CAD Storage user flow (upload / versioning / archiving) |  | 2025-08-22 | 2025-10-19 | Done | Medium
| M1-185 | Tony Ho |  | Add “Other” sub-level under Non-Drawing types |  | 2025-08-22 | 2025-10-19 | Done | Medium
| M1-184 | Tony Ho |  | Add “Other Doc” category under each Discipline |  | 2025-08-22 | 2025-10-19 | Done | Medium
| M1-183 | Cyrus Chau |  | Issue: files re-classified from “Unclassified” not updating to Archive |  | 2025-08-22 |  | Backlog | Medium
| M1-182 | Chung Edmond Tin Ho |  | AI Classification Review (prompt refinement) |  | 2025-08-22 | 2025-08-27 | Backlog | Medium
| M1-181 | Chung Edmond Tin Ho |  | Add Loading Screen |  | 2025-08-22 | 2025-08-25 | CLOSED | Medium
| M1-180 |  |  | Post-818 new request |  | 2025-08-22 | 2025-09-28 | Backlog | Medium
| M1-179 | Cyrus Chau |  | WebDAV Auto Delete Temp Folder Bug Fix |  | 2025-08-19 | 2025-08-20 | Done | Medium
| M1-178 | Cyrus Chau |  | WebDAV Service Email Alert when Task Failed |  | 2025-08-20 | 2025-08-21 | Done | Medium
| M1-177 | Cyrus Chau |  | SMTP Server Setup | TXTaliyundm.dev 48f8e4407e56a27145e7TXTdev v=spf1 include:spfdm-ap-southeast-1.aliyun.com -allTXTaliyun-ap-southeast-1._domainkey.dev v=DKIM1; k=rsa; p=MIGfMA0GCSqGSIb3DQEBAQUAA4GNADCBiQKBgQCjnvrhLc/6vonA4VZPjpxhS5asGBMLf8sweTW9W2uxioaVVF4ggYGKTPEH/7W2nlpg2sgfLg4om/rp566UBVjwo0ywiCCR2PVHWX8OmZwKQCP4YTwZV9sVmTHli3Nb37JDashxTkG12pEgx3wQj0ph2OReuF0lnSwmyEngaRqWIwIDAQABTXT_dmarc.dev v=DMARC1;p=none;rua=mailto:dmarc_report@service.aliyun.comMXdev mxdm-ap-southeast-1.aliyun.com | 2025-08-19 | 2025-08-21 | Done | Medium
| M1-176 |  |  | Issue: FTP WindowsExplorer Folder Name NOT same as File Path | Windows Explorerftp://webdav_sync@61.93.241.82:2121/wp-content/uploads/dms_drawings/2025-08-20-%25e9%25bb%2583%25e6%2596%25b0%25e8%2588%2588%25e4%25bd%258f%25e5%25ae%2585-batch-1/File (Right click Properties)ftp://webdav_sync@61.93.241.82:2121/wp-content/uploads/dms_drawings/2025-08-20-%e9%bb%83%e6%96%b0%e8%88%88%e4%bd%8f%e5%ae%85-batch-1/20221020-AI-MC-034.pdf | 2025-08-20 |  | Backlog | Medium
| M1-175 | Jazzy |  | 磁盘部署 和Team align-----香港部门，深圳部门，工厂部门，项目部公用一个磁盘 |  | 2025-08-19 | 2025-10-17 | Done | Medium
| M1-174 | Jazzy |  | Email Integration （场景确认） |  | 2025-08-19 | 2025-10-17 | Done | Medium
| M1-173 | Jazzy |  | Notification development（场景确认） |  | 2025-08-19 | 2025-09-25 | Done | Medium
| M1-172 | Jazzy |  | Specification Update |  | 2025-08-19 | 2025-08-20 | Done | Medium
| M1-171 | Chung Edmond Tin Ho |  | new endpoint to clean output files (outputs and static) |  | 2025-08-19 |  | In Progress | Medium
| M1-170 | Jazzy |  | 和李经理麻总confirm ROI的数字 |  | 2025-08-18 | 2025-09-25 | Done | Medium
| M1-169 | Jazzy |  | 制作Drawing submission workflow ，align with 李经理和麻总 |  | 2025-08-18 | 2025-09-25 | Done | Medium
| M1-168 | Jazzy |  | 更新“M1产品流程” |  | 2025-08-18 | 2025-08-20 | Done | Medium
| M1-167 | Jazzy |  | 找阿蔡要最新版本的“文件接受明细”，在进行优化 | 1-专业收窄2-每个专业的细分再加上“其他” | 2025-08-18 | 2025-08-24 | Done | Medium
| M1-166 | Tony Ho |  | Bug: Master Sheet -> Batch ID Column -> ID & Folder Path Not Align | How to Reproduce:After coordinator uploaded a new batchDrawing team confirmed new batchGo to master sheet look for the new “Live Design”The latest batch is 43, but in the related Batch ID column shows a different folder pathIn Master Sheet -> Batch ID Column, the ID & Folder Path Not Align. Pls reference attached image.Expected result: ID (Click-able) should be same as Folder Path | 2025-08-16 | 2025-10-19 | CLOSED | Medium
| M1-165 | Tony Ho |  | Bug: Date Receive Issue (Minor, Low-Priority) | The “Date Received” field show another non-related time.How to ReproduceIn Coordinator accountUpload a new batchAfter upload finish, check the “Date Received”There will be Some Chance to show a different older time than expect. | 2025-08-16 |  | Backlog | Medium
| M1-164 |  |  | LLM Api limit study, analyze tokens used on average |  | 2025-08-15 |  | Backlog | Medium
| M1-163 |  |  | Parallel n8n instances workflow study |  | 2025-08-15 |  | Backlog | Medium
| M1-162 |  |  | Modulize n8n functions |  | 2025-08-15 |  | Backlog | Medium
| M1-161 | Cyrus Chau |  | API study - CAD to PDF (Target covert to Vector Data base) |  | 2025-08-15 |  | Backlog | Medium
| M1-160 | Tony Ho |  | create drawing user view |  | 2025-08-14 | 2025-08-25 | Done | Medium
| M1-159 | Tony Ho |  | remove project type selection from coordinator view |  | 2025-08-14 | 2025-08-25 | Done | Medium

## Summary
Sprint Number | Alice | Ava | Daniel | David | Emily | John | Liam | Michael | Noah | Olivia | Sophia | Total
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0