## Tasks
Sprint Number | Task Number | Assignee | Team | Task Title | Task Description | Task start date | Task end date | Status | Priority | Story Point
1 | TK-1 | John | Business Analyst | Backlog refinement: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 8 SP. | 2025-01-06 | 2025-01-09 | Done | Critical | 8
1 | TK-2 | Olivia | QA | Test plan: Shop & IAP | QA task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-01-07 | 2025-01-09 | Done | Lowest | 3
1 | TK-3 | Sophia | Backend | Authentication/Session: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-01-07 | 2025-01-08 | Done | Medium | 3
1 | TK-4 | Liam | Data Team | Balance analysis: Social Sharing | Data Team task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-01-07 | 2025-01-08 | Done | High | 3
1 | TK-5 | Alice | Business Analyst | Backlog refinement: Live Ops Tooling | Business Analyst task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-01-07 | 2025-01-09 | Done | Medium | 3
1 | TK-6 | Noah | Frontend | UX polish: Localization | Frontend task for 'Localization'. Deliverable sized to 8 SP. | 2025-01-08 | 2025-01-13 | Done | Lowest | 8
1 | TK-7 | David | Frontend | Responsive layout: Guilds & Chat | Frontend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-01-08 | 2025-01-10 | Done | High | 5
1 | TK-8 | Sophia | Backend | Performance tuning: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-01-09 | 2025-01-11 | Done | High | 3
1 | TK-9 | Alice | Business Analyst | User stories: Weekly Boss Chase | Business Analyst task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-01-09 | 2025-01-10 | Done | Low | 5
1 | TK-10 | Emily | Frontend | UI integration test fixes: Inventory | Frontend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-01-09 | 2025-01-12 | Done | High | 5
1 | TK-11 | Sophia | Backend | API endpoint: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-01-09 | 2025-01-10 | Done | Critical | 3
1 | TK-12 | Michael | Backend | Game logic service: Weekly Boss Chase | Backend task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-01-09 | 2025-01-12 | Done | Lowest | 5
1 | TK-13 | Emily | Frontend | UX polish: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-01-10 | 2025-01-11 | Done | High | 5
1 | TK-14 | Olivia | QA | Test data setup: Inventory | QA task for 'Inventory'. Deliverable sized to 3 SP. | 2025-01-10 | 2025-01-11 | Done | Lowest | 3
1 | TK-15 | Daniel | QA | Test data setup: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-01-10 | 2025-01-11 | Done | High | 5
1 | TK-16 | Daniel | QA | Exploratory testing: Pet Companions | QA task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-01-11 | 2025-01-13 | Done | Low | 3
1 | TK-17 | Olivia | QA | Test plan: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-01-12 | 2025-01-13 | Done | Medium | 3
1 | TK-18 | Michael | Backend | Leaderboard/Guild service: Level Generator | Backend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-01-12 | 2025-01-15 | Done | Medium | 5
1 | TK-19 | Ava | Backend | Leaderboard/Guild service: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 8 SP. | 2025-01-12 | 2025-01-16 | Done | Lowest | 8
1 | TK-20 | Liam | Data Team | Balance analysis: Crafting & Upgrades | Data Team task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-01-15 | 2025-01-17 | Done | Medium | 3
1 | TK-21 | David | Frontend | Responsive layout: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-01-16 | 2025-01-17 | Done | Low | 3
1 | TK-22 | Liam | Data Team | ETL pipeline: Character Customization | Data Team task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-01-16 | 2025-01-18 | Done | Medium | 3
2 | TK-23 | Daniel | QA | Test data setup: Accessibility | QA task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-01-20 | 2025-01-24 | Done | Critical | 8
2 | TK-24 | Ava | Backend | API endpoint: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-01-20 | 2025-01-22 | Done | Lowest | 5
2 | TK-25 | Liam | Data Team | Event schema: Analytics & Telemetry | Data Team task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-01-20 | 2025-01-21 | Done | Medium | 3
2 | TK-26 | Emily | Frontend | Animations & VFX: Localization | Frontend task for 'Localization'. Deliverable sized to 5 SP. | 2025-01-21 | 2025-01-24 | Done | Medium | 5
2 | TK-27 | Sophia | Backend | Leaderboard/Guild service: Weekly Boss Chase | Backend task for 'Weekly Boss Chase'. Deliverable sized to 3 SP. | 2025-01-23 | 2025-01-24 | Done | Lowest | 3
2 | TK-28 | Ava | Backend | API endpoint: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-01-23 | 2025-01-24 | Done | Critical | 3
2 | TK-29 | David | Frontend | UI integration test fixes: Level Generator | Frontend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-01-23 | 2025-01-26 | Done | Lowest | 5
2 | TK-30 | Olivia | QA | Regression suite update: Inventory | QA task for 'Inventory'. Deliverable sized to 8 SP. | 2025-01-23 | 2025-01-25 | Done | Critical | 8
2 | TK-31 | John | Business Analyst | Acceptance criteria: Offline Mode | Business Analyst task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-01-23 | 2025-01-26 | Done | Medium | 8
2 | TK-32 | Liam | Data Team | Balance analysis: Weekly Boss Chase | Data Team task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-01-23 | 2025-01-24 | Done | Lowest | 5
2 | TK-33 | Noah | Frontend | Implement UI: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-01-23 | 2025-01-26 | Done | Critical | 8
2 | TK-34 | Alice | Business Analyst | Epic scoping: Shop & IAP | Business Analyst task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-01-24 | 2025-01-26 | Done | High | 3
2 | TK-35 | Michael | Backend | Leaderboard/Guild service: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-01-25 | 2025-01-27 | Done | Low | 3
2 | TK-36 | Sophia | Backend | API endpoint: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-01-25 | 2025-01-26 | Done | Lowest | 5
2 | TK-37 | Michael | Backend | Leaderboard/Guild service: Daily Challenges | Backend task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-01-26 | 2025-01-27 | Done | Medium | 5
2 | TK-38 | David | Frontend | Responsive layout: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-01-27 | 2025-01-29 | Done | Medium | 3
2 | TK-39 | Alice | Business Analyst | Acceptance criteria: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-01-28 | 2025-01-29 | Done | Medium | 3
2 | TK-40 | Emily | Frontend | Animations & VFX: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-01-28 | 2025-01-29 | Done | Lowest | 3
2 | TK-41 | Alice | Business Analyst | Epic scoping: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-01-30 | 2025-02-01 | Done | High | 3
3 | TK-42 | Daniel | QA | Test data setup: Core Runner Mechanics | QA task for 'Core Runner Mechanics'. Deliverable sized to 8 SP. | 2025-02-03 | 2025-02-07 | Done | Low | 8
3 | TK-43 | Olivia | QA | Functional test: Social Sharing | QA task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-02-03 | 2025-02-06 | Done | Critical | 5
3 | TK-44 | Noah | Frontend | Implement UI: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-02-03 | 2025-02-05 | Done | Low | 5
3 | TK-45 | Noah | Frontend | Implement UI: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-02-04 | 2025-02-05 | Done | Critical | 3
3 | TK-46 | Alice | Business Analyst | Epic scoping: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-02-05 | 2025-02-07 | Done | High | 5
3 | TK-47 | Ava | Backend | API endpoint: Power-ups & Boosts | Backend task for 'Power-ups & Boosts'. Deliverable sized to 8 SP. | 2025-02-05 | 2025-02-09 | Done | Medium | 8
3 | TK-48 | Emily | Frontend | UI integration test fixes: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 8 SP. | 2025-02-06 | 2025-02-08 | Done | Medium | 8
3 | TK-49 | Sophia | Backend | API endpoint: Inventory | Backend task for 'Inventory'. Deliverable sized to 8 SP. | 2025-02-06 | 2025-02-10 | Done | Medium | 8
3 | TK-50 | David | Frontend | Responsive layout: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-02-07 | 2025-02-08 | Done | Critical | 5
3 | TK-51 | David | Frontend | UX polish: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-02-07 | 2025-02-09 | Done | High | 3
3 | TK-52 | John | Business Analyst | Stakeholder workshop: Beta Release | Business Analyst task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-02-07 | 2025-02-09 | Done | Critical | 5
3 | TK-53 | Liam | Data Team | ETL pipeline: Shop & IAP | Data Team task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-02-07 | 2025-02-12 | Done | Critical | 8
3 | TK-54 | Alice | Business Analyst | Stakeholder workshop: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 5 SP. | 2025-02-10 | 2025-02-12 | Done | Lowest | 5
3 | TK-55 | John | Business Analyst | Backlog refinement: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-02-10 | 2025-02-11 | Done | Low | 5
3 | TK-56 | Michael | Backend | Performance tuning: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-02-11 | 2025-02-12 | Done | Lowest | 5
3 | TK-57 | Olivia | QA | Test plan: Pet Companions | QA task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-02-12 | 2025-02-13 | Done | Critical | 3
3 | TK-58 | Michael | Backend | Authentication/Session: Analytics & Telemetry | Backend task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-02-13 | 2025-02-14 | Done | Lowest | 3
4 | TK-59 | Emily | Frontend | Animations & VFX: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-02-17 | 2025-02-19 | Done | Medium | 5
4 | TK-60 | John | Business Analyst | Epic scoping: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-02-18 | 2025-02-19 | Done | High | 5
4 | TK-61 | Olivia | QA | Exploratory testing: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-02-19 | 2025-02-20 | Done | Critical | 5
4 | TK-62 | Ava | Backend | Performance tuning: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 8 SP. | 2025-02-20 | 2025-02-24 | Done | High | 8
4 | TK-63 | David | Frontend | UX polish: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-02-20 | 2025-02-21 | Done | Critical | 5
4 | TK-64 | Emily | Frontend | UX polish: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-02-21 | 2025-02-22 | Done | Critical | 5
4 | TK-65 | Sophia | Backend | Game logic service: Weekly Boss Chase | Backend task for 'Weekly Boss Chase'. Deliverable sized to 8 SP. | 2025-02-21 | 2025-02-23 | Done | High | 8
4 | TK-66 | David | Frontend | Responsive layout: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-02-21 | 2025-02-22 | Done | Medium | 3
4 | TK-67 | Daniel | QA | Test plan: Character Customization | QA task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-02-21 | 2025-02-23 | Done | Critical | 5
4 | TK-68 | Alice | Business Analyst | Stakeholder workshop: Offline Mode | Business Analyst task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-02-21 | 2025-02-22 | Done | Medium | 5
4 | TK-69 | Liam | Data Team | A/B experiment design: Season Pass | Data Team task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-02-21 | 2025-02-23 | Done | Low | 3
4 | TK-70 | Michael | Backend | Game logic service: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-02-21 | 2025-02-22 | Done | Medium | 5
4 | TK-71 | Liam | Data Team | A/B experiment design: Shop & IAP | Data Team task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-02-22 | 2025-02-23 | Done | Lowest | 3
4 | TK-72 | Daniel | QA | Test plan: Beta Release | QA task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-02-22 | 2025-02-23 | Done | Medium | 3
4 | TK-73 | Olivia | QA | Functional test: Beta Release | QA task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-02-23 | 2025-02-24 | Done | Medium | 3
4 | TK-74 | Noah | Frontend | UI integration test fixes: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-02-23 | 2025-02-27 | Done | Critical | 8
4 | TK-75 | Michael | Backend | Leaderboard/Guild service: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-02-25 | 2025-02-26 | Done | Low | 5
4 | TK-76 | John | Business Analyst | User stories: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-02-25 | 2025-02-26 | Done | Critical | 5
4 | TK-77 | Liam | Data Team | Dashboard build: A/B Testing Framework | Data Team task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-02-25 | 2025-02-26 | Done | High | 3
4 | TK-78 | Alice | Business Analyst | User stories: Accessibility | Business Analyst task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-02-27 | 2025-03-01 | Done | High | 3
5 | TK-79 | David | Frontend | Animations & VFX: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-03-03 | 2025-03-04 | Done | Low | 3
5 | TK-80 | Liam | Data Team | Balance analysis: Leaderboard | Data Team task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-03-03 | 2025-03-08 | Done | High | 8
5 | TK-81 | Daniel | QA | Test plan: Character Customization | QA task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-03-03 | 2025-03-04 | Done | Medium | 3
5 | TK-82 | John | Business Analyst | User stories: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-03-04 | 2025-03-06 | Done | High | 5
5 | TK-83 | Ava | Backend | Leaderboard/Guild service: Daily Challenges | Backend task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-03-05 | 2025-03-08 | Done | Lowest | 5
5 | TK-84 | David | Frontend | Animations & VFX: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-03-05 | 2025-03-07 | Done | High | 3
5 | TK-85 | Olivia | QA | Exploratory testing: Push Notifications | QA task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-03-06 | 2025-03-07 | Done | Critical | 5
5 | TK-86 | Olivia | QA | Exploratory testing: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-03-06 | 2025-03-09 | Done | High | 5
5 | TK-87 | Michael | Backend | Game logic service: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-03-07 | 2025-03-11 | Done | Critical | 8
5 | TK-88 | Daniel | QA | Functional test: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-03-07 | 2025-03-08 | Done | High | 5
5 | TK-89 | Alice | Business Analyst | Acceptance criteria: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-03-07 | 2025-03-08 | Done | High | 3
5 | TK-90 | Noah | Frontend | Animations & VFX: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-03-07 | 2025-03-08 | Done | Lowest | 3
5 | TK-91 | Alice | Business Analyst | User stories: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-03-07 | 2025-03-09 | Done | High | 5
5 | TK-92 | Ava | Backend | Leaderboard/Guild service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-03-08 | 2025-03-10 | Done | Medium | 3
5 | TK-93 | David | Frontend | UI integration test fixes: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-03-08 | 2025-03-10 | Done | High | 3
5 | TK-94 | Emily | Frontend | Implement UI: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-03-09 | 2025-03-12 | Done | Lowest | 8
5 | TK-95 | Noah | Frontend | UI integration test fixes: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-03-10 | 2025-03-11 | Done | High | 5
5 | TK-96 | John | Business Analyst | Stakeholder workshop: Guilds & Chat | Business Analyst task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-03-10 | 2025-03-13 | Done | High | 5
5 | TK-97 | Sophia | Backend | Performance tuning: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-03-10 | 2025-03-13 | Done | Medium | 8
6 | TK-98 | Daniel | QA | Test data setup: Localization | QA task for 'Localization'. Deliverable sized to 3 SP. | 2025-03-17 | 2025-03-19 | Done | Low | 3
6 | TK-99 | Olivia | QA | Test plan: Offline Mode | QA task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-03-17 | 2025-03-20 | Done | Critical | 8
6 | TK-100 | Sophia | Backend | Game logic service: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 8 SP. | 2025-03-18 | 2025-03-22 | Done | Critical | 8
6 | TK-101 | David | Frontend | Implement UI: Localization | Frontend task for 'Localization'. Deliverable sized to 3 SP. | 2025-03-19 | 2025-03-21 | Done | Low | 3
6 | TK-102 | Alice | Business Analyst | Stakeholder workshop: Live Ops Tooling | Business Analyst task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-03-19 | 2025-03-21 | Done | Medium | 3
6 | TK-103 | Emily | Frontend | UX polish: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 8 SP. | 2025-03-19 | 2025-03-24 | Done | High | 8
6 | TK-104 | John | Business Analyst | Acceptance criteria: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-03-20 | 2025-03-22 | Done | Low | 3
6 | TK-105 | Liam | Data Team | Balance analysis: Guilds & Chat | Data Team task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-03-21 | 2025-03-23 | Done | Lowest | 5
6 | TK-106 | Liam | Data Team | Event schema: Launch & Post-Launch | Data Team task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-03-21 | 2025-03-23 | Done | Low | 5
6 | TK-107 | Daniel | QA | Exploratory testing: Accessibility | QA task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-03-21 | 2025-03-22 | Done | Low | 5
6 | TK-108 | David | Frontend | Responsive layout: A/B Testing Framework | Frontend task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-03-22 | 2025-03-23 | Done | Medium | 5
6 | TK-109 | Michael | Backend | API endpoint: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-03-22 | 2025-03-25 | Done | Lowest | 5
6 | TK-110 | John | Business Analyst | Epic scoping: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-03-23 | 2025-03-24 | Done | Lowest | 3
6 | TK-111 | Alice | Business Analyst | Stakeholder workshop: Season Pass | Business Analyst task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-03-23 | 2025-03-24 | Done | High | 3
6 | TK-112 | Noah | Frontend | UI integration test fixes: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-03-23 | 2025-03-28 | Done | Lowest | 8
6 | TK-113 | John | Business Analyst | User stories: Leaderboard | Business Analyst task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-03-24 | 2025-03-25 | Done | Lowest | 3
6 | TK-114 | Ava | Backend | Authentication/Session: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-03-24 | 2025-03-27 | Done | Critical | 5
6 | TK-115 | Alice | Business Analyst | Stakeholder workshop: Weekly Boss Chase | Business Analyst task for 'Weekly Boss Chase'. Deliverable sized to 3 SP. | 2025-03-24 | 2025-03-25 | Done | Medium | 3
6 | TK-116 | Michael | Backend | API endpoint: Inventory | Backend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-03-25 | 2025-03-27 | Done | High | 3
6 | TK-117 | Ava | Backend | Performance tuning: Pet Companions | Backend task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-03-27 | 2025-03-29 | Done | Critical | 3
7 | TK-118 | David | Frontend | Responsive layout: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-03-31 | 2025-04-01 | Done | Low | 3
7 | TK-119 | Alice | Business Analyst | Acceptance criteria: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-03-31 | 2025-04-02 | Done | Low | 5
7 | TK-120 | Ava | Backend | Authentication/Session: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-03-31 | 2025-04-03 | Done | Critical | 5
7 | TK-121 | Sophia | Backend | API endpoint: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 8 SP. | 2025-04-01 | 2025-04-06 | Done | Medium | 8
7 | TK-122 | Noah | Frontend | Animations & VFX: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-04-01 | 2025-04-02 | Done | Lowest | 5
7 | TK-123 | Emily | Frontend | UI integration test fixes: Localization | Frontend task for 'Localization'. Deliverable sized to 5 SP. | 2025-04-02 | 2025-04-03 | Done | Medium | 5
7 | TK-124 | John | Business Analyst | Epic scoping: Level Generator | Business Analyst task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-04-03 | 2025-04-06 | Done | Lowest | 5
7 | TK-125 | Liam | Data Team | ETL pipeline: Accessibility | Data Team task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-04-03 | 2025-04-07 | Done | Low | 8
7 | TK-126 | Daniel | QA | Exploratory testing: Daily Challenges | QA task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-04-03 | 2025-04-05 | Done | Lowest | 3
7 | TK-127 | Alice | Business Analyst | Stakeholder workshop: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 5 SP. | 2025-04-03 | 2025-04-05 | Done | Lowest | 5
7 | TK-128 | Michael | Backend | Game logic service: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-04-04 | 2025-04-05 | Done | High | 5
7 | TK-129 | David | Frontend | UX polish: Inventory | Frontend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-04-04 | 2025-04-05 | Done | Lowest | 5
7 | TK-130 | Olivia | QA | Regression suite update: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-04-04 | 2025-04-06 | Done | Medium | 3
7 | TK-131 | Michael | Backend | Performance tuning: Power-ups & Boosts | Backend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-04-06 | 2025-04-09 | Done | Critical | 5
7 | TK-132 | Ava | Backend | Leaderboard/Guild service: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-04-07 | 2025-04-09 | Done | Low | 5
7 | TK-133 | Daniel | QA | Exploratory testing: Push Notifications | QA task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-04-07 | 2025-04-08 | Done | Lowest | 5
7 | TK-134 | Noah | Frontend | Animations & VFX: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-04-07 | 2025-04-09 | Done | High | 3
7 | TK-135 | John | Business Analyst | Acceptance criteria: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-04-08 | 2025-04-09 | Done | Lowest | 5
7 | TK-136 | Olivia | QA | Exploratory testing: Inventory | QA task for 'Inventory'. Deliverable sized to 5 SP. | 2025-04-08 | 2025-04-10 | Done | High | 5
7 | TK-137 | Emily | Frontend | Responsive layout: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-04-09 | 2025-04-11 | Done | High | 3
8 | TK-138 | David | Frontend | UX polish: Obstacle Library | Frontend task for 'Obstacle Library'. Deliverable sized to 8 SP. | 2025-04-14 | 2025-04-18 | Done | Low | 8
8 | TK-139 | Ava | Backend | Leaderboard/Guild service: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-04-14 | 2025-04-15 | Done | Medium | 3
8 | TK-140 | Noah | Frontend | Animations & VFX: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-04-15 | 2025-04-17 | Done | High | 3
8 | TK-141 | Alice | Business Analyst | Backlog refinement: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 8 SP. | 2025-04-15 | 2025-04-18 | Done | Low | 8
8 | TK-142 | John | Business Analyst | Stakeholder workshop: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-04-15 | 2025-04-16 | Done | Medium | 3
8 | TK-143 | John | Business Analyst | Epic scoping: Season Pass | Business Analyst task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-04-17 | 2025-04-19 | Done | High | 5
8 | TK-144 | Olivia | QA | Test data setup: Season Pass | QA task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-04-18 | 2025-04-23 | Done | Low | 8
8 | TK-145 | Daniel | QA | Functional test: Offline Mode | QA task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-04-18 | 2025-04-19 | Done | Low | 5
8 | TK-146 | Noah | Frontend | Animations & VFX: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-04-18 | 2025-04-19 | Done | Lowest | 5
8 | TK-147 | Ava | Backend | Performance tuning: Level Generator | Backend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-04-19 | 2025-04-22 | Done | High | 5
8 | TK-148 | Sophia | Backend | Authentication/Session: Pet Companions | Backend task for 'Pet Companions'. Deliverable sized to 5 SP. | 2025-04-20 | 2025-04-23 | Done | Critical | 5
8 | TK-149 | Michael | Backend | API endpoint: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-04-20 | 2025-04-22 | Done | High | 8
8 | TK-150 | Emily | Frontend | Implement UI: Cloud Save | Frontend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-04-20 | 2025-04-23 | Done | Critical | 5
8 | TK-151 | Daniel | QA | Functional test: Live Ops Tooling | QA task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-04-20 | 2025-04-21 | Done | Low | 5
8 | TK-152 | Liam | Data Team | Balance analysis: Season Pass | Data Team task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-04-21 | 2025-04-23 | Done | Low | 8
8 | TK-153 | Emily | Frontend | UI integration test fixes: Weekly Boss Chase | Frontend task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-04-22 | 2025-04-24 | Done | Critical | 5
8 | TK-154 | Sophia | Backend | Leaderboard/Guild service: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-04-22 | 2025-04-23 | Done | Critical | 5
9 | TK-155 | Sophia | Backend | API endpoint: Guilds & Chat | Backend task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-04-30 | 2025-05-02 | Done | Lowest | 3
9 | TK-156 | Olivia | QA | Test data setup: Level Generator | QA task for 'Level Generator'. Deliverable sized to 8 SP. | 2025-04-30 | 2025-05-02 | Done | Medium | 8
9 | TK-157 | Ava | Backend | Authentication/Session: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 8 SP. | 2025-05-01 | 2025-05-03 | Done | Medium | 8
9 | TK-158 | David | Frontend | UX polish: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-05-01 | 2025-05-03 | Done | Medium | 3
9 | TK-159 | Alice | Business Analyst | Epic scoping: Leaderboard | Business Analyst task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-05-01 | 2025-05-02 | Done | High | 5
9 | TK-160 | Emily | Frontend | UI integration test fixes: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-05-02 | 2025-05-03 | Done | Lowest | 5
9 | TK-161 | Alice | Business Analyst | User stories: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-05-02 | 2025-05-05 | Done | Lowest | 5
9 | TK-162 | Noah | Frontend | Animations & VFX: Localization | Frontend task for 'Localization'. Deliverable sized to 5 SP. | 2025-05-04 | 2025-05-06 | Done | Low | 5
9 | TK-163 | Michael | Backend | Performance tuning: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-05-04 | 2025-05-06 | Done | Lowest | 5
9 | TK-164 | Liam | Data Team | Event schema: Offline Mode | Data Team task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-05-05 | 2025-05-08 | Done | Medium | 8
9 | TK-165 | John | Business Analyst | User stories: Launch & Post-Launch | Business Analyst task for 'Launch & Post-Launch'. Deliverable sized to 8 SP. | 2025-05-05 | 2025-05-09 | Done | Medium | 8
9 | TK-166 | Noah | Frontend | UX polish: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-05-05 | 2025-05-06 | Done | High | 3
9 | TK-167 | Sophia | Backend | API endpoint: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-05-05 | 2025-05-06 | Done | Lowest | 3
9 | TK-168 | Daniel | QA | Exploratory testing: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 8 SP. | 2025-05-05 | 2025-05-08 | Done | Critical | 8
9 | TK-169 | Sophia | Backend | API endpoint: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-05-05 | 2025-05-07 | Done | Lowest | 3
9 | TK-170 | David | Frontend | UI integration test fixes: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-05-06 | 2025-05-08 | Done | High | 5
9 | TK-171 | Michael | Backend | Leaderboard/Guild service: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-05-06 | 2025-05-07 | Done | Critical | 5
9 | TK-172 | Emily | Frontend | UI integration test fixes: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-05-07 | 2025-05-09 | Done | Critical | 3
10 | TK-173 | David | Frontend | UI integration test fixes: Onboarding & Tutorial | Frontend task for 'Onboarding & Tutorial'. Deliverable sized to 5 SP. | 2025-05-12 | 2025-05-15 | Done | Critical | 5
10 | TK-174 | Emily | Frontend | Animations & VFX: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-05-13 | 2025-05-14 | Done | Lowest | 5
10 | TK-175 | Noah | Frontend | UX polish: Weekly Boss Chase | Frontend task for 'Weekly Boss Chase'. Deliverable sized to 8 SP. | 2025-05-13 | 2025-05-15 | Done | Lowest | 8
10 | TK-176 | Sophia | Backend | Game logic service: Localization | Backend task for 'Localization'. Deliverable sized to 5 SP. | 2025-05-13 | 2025-05-15 | Done | Medium | 5
10 | TK-177 | Michael | Backend | Authentication/Session: Social Sharing | Backend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-05-14 | 2025-05-16 | Done | Low | 5
10 | TK-178 | John | Business Analyst | Backlog refinement: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-05-14 | 2025-05-15 | Done | Medium | 3
10 | TK-179 | Sophia | Backend | Game logic service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-05-15 | 2025-05-16 | Done | Low | 3
10 | TK-180 | David | Frontend | Responsive layout: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 3 SP. | 2025-05-15 | 2025-05-17 | Done | Critical | 3
10 | TK-181 | Alice | Business Analyst | Epic scoping: Beta Release | Business Analyst task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-05-16 | 2025-05-18 | Done | Critical | 5
10 | TK-182 | Emily | Frontend | UI integration test fixes: Inventory | Frontend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-05-16 | 2025-05-18 | Done | High | 3
10 | TK-183 | Olivia | QA | Regression suite update: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 8 SP. | 2025-05-16 | 2025-05-21 | Done | High | 8
10 | TK-184 | Liam | Data Team | Balance analysis: Power-ups & Boosts | Data Team task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-05-17 | 2025-05-20 | Done | Critical | 5
10 | TK-185 | Michael | Backend | Authentication/Session: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-05-17 | 2025-05-18 | Done | Critical | 3
10 | TK-186 | Liam | Data Team | A/B experiment design: Weekly Boss Chase | Data Team task for 'Weekly Boss Chase'. Deliverable sized to 3 SP. | 2025-05-18 | 2025-05-20 | Done | Medium | 3
10 | TK-187 | Ava | Backend | Game logic service: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-05-18 | 2025-05-22 | Done | Low | 8
10 | TK-188 | John | Business Analyst | Backlog refinement: Obstacle Library | Business Analyst task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-05-18 | 2025-05-21 | Done | Critical | 5
10 | TK-189 | Daniel | QA | Test plan: Weekly Boss Chase | QA task for 'Weekly Boss Chase'. Deliverable sized to 8 SP. | 2025-05-19 | 2025-05-23 | Done | Low | 8
10 | TK-190 | Alice | Business Analyst | User stories: Character Customization | Business Analyst task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-05-20 | 2025-05-22 | Done | Lowest | 3
11 | TK-191 | Noah | Frontend | UX polish: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-05-26 | 2025-05-28 | Done | High | 5
11 | TK-192 | Sophia | Backend | Game logic service: Onboarding & Tutorial | Backend task for 'Onboarding & Tutorial'. Deliverable sized to 8 SP. | 2025-05-26 | 2025-05-30 | Done | Lowest | 8
11 | TK-193 | Olivia | QA | Regression suite update: Daily Challenges | QA task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-05-27 | 2025-05-30 | Done | Lowest | 5
11 | TK-194 | Ava | Backend | Performance tuning: Social Sharing | Backend task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-05-27 | 2025-05-29 | Done | High | 3
11 | TK-195 | Emily | Frontend | Animations & VFX: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-05-27 | 2025-05-30 | Done | Lowest | 5
11 | TK-196 | Michael | Backend | API endpoint: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-05-28 | 2025-06-01 | Done | Medium | 8
11 | TK-197 | David | Frontend | Responsive layout: Core Runner Mechanics | Frontend task for 'Core Runner Mechanics'. Deliverable sized to 5 SP. | 2025-05-29 | 2025-05-30 | Done | Medium | 5
11 | TK-198 | Liam | Data Team | A/B experiment design: Core Runner Mechanics | Data Team task for 'Core Runner Mechanics'. Deliverable sized to 3 SP. | 2025-05-30 | 2025-06-01 | Done | Lowest | 3
11 | TK-199 | Emily | Frontend | Animations & VFX: Core Runner Mechanics | Frontend task for 'Core Runner Mechanics'. Deliverable sized to 5 SP. | 2025-05-30 | 2025-05-31 | Done | Low | 5
11 | TK-200 | Alice | Business Analyst | Backlog refinement: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 8 SP. | 2025-05-31 | 2025-06-03 | Done | Critical | 8
11 | TK-201 | Olivia | QA | Test plan: Weekly Boss Chase | QA task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-05-31 | 2025-06-01 | Done | Medium | 5
11 | TK-202 | John | Business Analyst | Acceptance criteria: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-06-01 | 2025-06-02 | Done | Lowest | 5
11 | TK-203 | Daniel | QA | Functional test: Localization | QA task for 'Localization'. Deliverable sized to 3 SP. | 2025-06-01 | 2025-06-02 | Done | Medium | 3
11 | TK-204 | John | Business Analyst | Acceptance criteria: Core Runner Mechanics | Business Analyst task for 'Core Runner Mechanics'. Deliverable sized to 3 SP. | 2025-06-02 | 2025-06-03 | Done | Critical | 3
11 | TK-205 | Liam | Data Team | Balance analysis: Power-ups & Boosts | Data Team task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-06-02 | 2025-06-03 | Done | Critical | 3
11 | TK-206 | Ava | Backend | API endpoint: Localization | Backend task for 'Localization'. Deliverable sized to 5 SP. | 2025-06-02 | 2025-06-04 | Done | Lowest | 5
11 | TK-207 | Liam | Data Team | Event schema: Onboarding & Tutorial | Data Team task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-06-02 | 2025-06-04 | Done | High | 3
11 | TK-208 | David | Frontend | Implement UI: Level Generator | Frontend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-06-03 | 2025-06-04 | Done | Low | 5
11 | TK-209 | Noah | Frontend | UX polish: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-06-03 | 2025-06-05 | Done | Low | 3
11 | TK-210 | Daniel | QA | Regression suite update: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-06-03 | 2025-06-05 | Done | Critical | 5
12 | TK-211 | Sophia | Backend | Authentication/Session: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-06-09 | 2025-06-10 | Done | Lowest | 5
12 | TK-212 | Liam | Data Team | A/B experiment design: Accessibility | Data Team task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-06-09 | 2025-06-10 | Done | Lowest | 3
12 | TK-213 | Liam | Data Team | Dashboard build: Localization | Data Team task for 'Localization'. Deliverable sized to 5 SP. | 2025-06-10 | 2025-06-11 | Done | Lowest | 5
12 | TK-214 | Noah | Frontend | Responsive layout: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-06-10 | 2025-06-12 | Done | Lowest | 3
12 | TK-215 | Emily | Frontend | Implement UI: Obstacle Library | Frontend task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-06-10 | 2025-06-12 | Done | Medium | 5
12 | TK-216 | John | Business Analyst | Stakeholder workshop: Cloud Save | Business Analyst task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-06-10 | 2025-06-13 | Done | Lowest | 5
12 | TK-217 | Emily | Frontend | Responsive layout: Localization | Frontend task for 'Localization'. Deliverable sized to 3 SP. | 2025-06-11 | 2025-06-12 | Done | Low | 3
12 | TK-218 | Alice | Business Analyst | Epic scoping: Character Customization | Business Analyst task for 'Character Customization'. Deliverable sized to 8 SP. | 2025-06-11 | 2025-06-15 | Done | Low | 8
12 | TK-219 | Michael | Backend | API endpoint: Inventory | Backend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-06-11 | 2025-06-12 | Done | Lowest | 5
12 | TK-220 | Michael | Backend | API endpoint: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-06-11 | 2025-06-14 | Done | High | 5
12 | TK-221 | Ava | Backend | Performance tuning: Localization | Backend task for 'Localization'. Deliverable sized to 8 SP. | 2025-06-12 | 2025-06-17 | Done | Lowest | 8
12 | TK-222 | Noah | Frontend | Animations & VFX: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-06-12 | 2025-06-13 | Done | Low | 5
12 | TK-223 | David | Frontend | Implement UI: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-06-13 | 2025-06-15 | Done | Critical | 3
12 | TK-224 | Olivia | QA | Regression suite update: Leaderboard | QA task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-06-13 | 2025-06-17 | Done | Critical | 8
12 | TK-225 | David | Frontend | Animations & VFX: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-06-14 | 2025-06-17 | Done | Medium | 5
12 | TK-226 | Daniel | QA | Functional test: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-06-15 | 2025-06-17 | Done | Critical | 5
12 | TK-227 | Daniel | QA | Regression suite update: Leaderboard | QA task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-06-16 | 2025-06-18 | Done | Low | 5
12 | TK-228 | John | Business Analyst | Backlog refinement: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-06-17 | 2025-06-19 | Done | Lowest | 5
12 | TK-229 | Sophia | Backend | Performance tuning: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-06-17 | 2025-06-18 | Done | High | 5
13 | TK-230 | John | Business Analyst | Acceptance criteria: Live Ops Tooling | Business Analyst task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-06-23 | 2025-06-24 | Done | Medium | 5
13 | TK-231 | John | Business Analyst | Epic scoping: Cloud Save | Business Analyst task for 'Cloud Save'. Deliverable sized to 3 SP. | 2025-06-23 | 2025-06-24 | Done | Lowest | 3
13 | TK-232 | David | Frontend | Responsive layout: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-06-24 | 2025-06-26 | Done | High | 5
13 | TK-233 | Liam | Data Team | Dashboard build: Inventory | Data Team task for 'Inventory'. Deliverable sized to 3 SP. | 2025-06-24 | 2025-06-25 | Done | Medium | 3
13 | TK-234 | Emily | Frontend | Animations & VFX: Onboarding & Tutorial | Frontend task for 'Onboarding & Tutorial'. Deliverable sized to 8 SP. | 2025-06-24 | 2025-06-28 | Done | Low | 8
13 | TK-235 | Olivia | QA | Regression suite update: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-06-24 | 2025-06-26 | Done | Critical | 3
13 | TK-236 | Michael | Backend | Game logic service: Level Generator | Backend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-06-25 | 2025-06-28 | Done | Critical | 5
13 | TK-237 | Michael | Backend | Game logic service: Launch & Post-Launch | Backend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-06-26 | 2025-06-27 | Done | Critical | 5
13 | TK-238 | Alice | Business Analyst | Stakeholder workshop: Guilds & Chat | Business Analyst task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-06-27 | 2025-06-28 | Done | Lowest | 5
13 | TK-239 | Daniel | QA | Regression suite update: Character Customization | QA task for 'Character Customization'. Deliverable sized to 8 SP. | 2025-06-27 | 2025-07-01 | Done | Medium | 8
13 | TK-240 | Sophia | Backend | Game logic service: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-06-28 | 2025-06-29 | Done | Lowest | 5
13 | TK-241 | Ava | Backend | Performance tuning: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-06-28 | 2025-06-30 | Done | Medium | 3
13 | TK-242 | Noah | Frontend | UX polish: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 8 SP. | 2025-06-29 | 2025-07-04 | Done | Low | 8
13 | TK-243 | Alice | Business Analyst | Acceptance criteria: Power-ups & Boosts | Business Analyst task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-06-29 | 2025-06-30 | Done | Lowest | 3
13 | TK-244 | Ava | Backend | Leaderboard/Guild service: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-06-30 | 2025-07-02 | Done | Lowest | 3
13 | TK-245 | David | Frontend | UX polish: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-06-30 | 2025-07-03 | Done | Low | 5
13 | TK-246 | Liam | Data Team | Dashboard build: Obstacle Library | Data Team task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-06-30 | 2025-07-02 | Done | Low | 5
13 | TK-247 | Ava | Backend | Leaderboard/Guild service: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-06-30 | 2025-07-02 | Done | Low | 3
13 | TK-248 | Sophia | Backend | API endpoint: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-07-01 | 2025-07-02 | Done | Critical | 3
13 | TK-249 | Olivia | QA | Exploratory testing: Character Customization | QA task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-07-01 | 2025-07-04 | Done | Medium | 5
14 | TK-250 | Noah | Frontend | Implement UI: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-07-07 | 2025-07-11 | Done | Critical | 8
14 | TK-251 | John | Business Analyst | Acceptance criteria: Launch & Post-Launch | Business Analyst task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-07-08 | 2025-07-11 | Done | Medium | 5
14 | TK-252 | Daniel | QA | Regression suite update: Core Runner Mechanics | QA task for 'Core Runner Mechanics'. Deliverable sized to 3 SP. | 2025-07-08 | 2025-07-10 | Done | Low | 3
14 | TK-253 | Emily | Frontend | Responsive layout: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-07-09 | 2025-07-10 | Done | Medium | 3
14 | TK-254 | Sophia | Backend | Game logic service: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-07-09 | 2025-07-12 | Done | Medium | 5
14 | TK-255 | David | Frontend | Responsive layout: Inventory | Frontend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-07-09 | 2025-07-10 | Done | High | 5
14 | TK-256 | Liam | Data Team | A/B experiment design: Level Generator | Data Team task for 'Level Generator'. Deliverable sized to 8 SP. | 2025-07-09 | 2025-07-13 | Done | Medium | 8
14 | TK-257 | Olivia | QA | Test data setup: Localization | QA task for 'Localization'. Deliverable sized to 5 SP. | 2025-07-09 | 2025-07-11 | Done | High | 5
14 | TK-258 | David | Frontend | Animations & VFX: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-07-10 | 2025-07-11 | Done | High | 3
14 | TK-259 | Michael | Backend | Performance tuning: Daily Challenges | Backend task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-07-10 | 2025-07-12 | Done | High | 3
14 | TK-260 | Michael | Backend | Performance tuning: Guilds & Chat | Backend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-07-11 | 2025-07-14 | Done | Lowest | 5
14 | TK-261 | Emily | Frontend | Implement UI: Cloud Save | Frontend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-07-11 | 2025-07-14 | Done | Low | 5
14 | TK-262 | Olivia | QA | Functional test: Live Ops Tooling | QA task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-07-12 | 2025-07-14 | Done | High | 3
14 | TK-263 | Daniel | QA | Exploratory testing: Season Pass | QA task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-07-13 | 2025-07-15 | Done | Lowest | 5
14 | TK-264 | John | Business Analyst | User stories: Core Runner Mechanics | Business Analyst task for 'Core Runner Mechanics'. Deliverable sized to 5 SP. | 2025-07-14 | 2025-07-16 | Done | Low | 5
14 | TK-265 | Alice | Business Analyst | Epic scoping: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-07-14 | 2025-07-17 | Done | Medium | 5
14 | TK-266 | Ava | Backend | Authentication/Session: Level Generator | Backend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-07-14 | 2025-07-16 | Done | Critical | 5
14 | TK-267 | Sophia | Backend | Game logic service: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-07-14 | 2025-07-15 | Done | Critical | 3
14 | TK-268 | Alice | Business Analyst | Backlog refinement: Shop & IAP | Business Analyst task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-07-14 | 2025-07-15 | Done | Low | 3
14 | TK-269 | Ava | Backend | Leaderboard/Guild service: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-07-15 | 2025-07-18 | Done | High | 5
15 | TK-270 | Ava | Backend | Leaderboard/Guild service: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-07-21 | 2025-07-25 | Done | High | 8
15 | TK-271 | Sophia | Backend | Authentication/Session: Inventory | Backend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-07-21 | 2025-07-23 | Done | Low | 5
15 | TK-272 | Noah | Frontend | UX polish: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-07-22 | 2025-07-25 | Done | Critical | 5
15 | TK-273 | Emily | Frontend | Animations & VFX: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-07-22 | 2025-07-24 | Done | Critical | 5
15 | TK-274 | Sophia | Backend | Game logic service: Inventory | Backend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-07-22 | 2025-07-25 | Done | Lowest | 5
15 | TK-275 | Alice | Business Analyst | Backlog refinement: Power-ups & Boosts | Business Analyst task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-07-22 | 2025-07-24 | Done | Medium | 5
15 | TK-276 | Michael | Backend | Authentication/Session: Analytics & Telemetry | Backend task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-07-23 | 2025-07-26 | Done | High | 5
15 | TK-277 | Daniel | QA | Regression suite update: Power-ups & Boosts | QA task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-07-23 | 2025-07-24 | Done | High | 3
15 | TK-278 | David | Frontend | UX polish: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-07-23 | 2025-07-25 | Done | High | 3
15 | TK-279 | Emily | Frontend | Implement UI: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-07-24 | 2025-07-26 | Done | Critical | 5
15 | TK-280 | Olivia | QA | Test plan: Obstacle Library | QA task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-07-25 | 2025-07-26 | Done | High | 3
15 | TK-281 | Liam | Data Team | Balance analysis: Analytics & Telemetry | Data Team task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-07-25 | 2025-07-26 | Done | Medium | 5
15 | TK-282 | Daniel | QA | Test plan: Crafting & Upgrades | QA task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-07-26 | 2025-07-27 | Done | Medium | 5
15 | TK-283 | John | Business Analyst | Stakeholder workshop: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 8 SP. | 2025-07-26 | 2025-07-28 | Done | Medium | 8
15 | TK-284 | Olivia | QA | Functional test: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-07-28 | 2025-07-30 | Done | High | 5
15 | TK-285 | Alice | Business Analyst | Acceptance criteria: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-07-28 | 2025-07-29 | Done | High | 3
15 | TK-286 | Liam | Data Team | Dashboard build: Shop & IAP | Data Team task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-07-29 | 2025-07-31 | Done | Critical | 5
15 | TK-287 | Noah | Frontend | UI integration test fixes: Obstacle Library | Frontend task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-07-29 | 2025-07-30 | Done | Low | 3
15 | TK-288 | David | Frontend | Animations & VFX: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-07-29 | 2025-07-30 | Done | Low | 5
15 | TK-289 | Michael | Backend | Leaderboard/Guild service: A/B Testing Framework | Backend task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-07-31 | 2025-08-01 | Done | Low | 3
16 | TK-290 | David | Frontend | UX polish: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-08-04 | 2025-08-05 | Done | Medium | 3
16 | TK-291 | Noah | Frontend | UI integration test fixes: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-08-04 | 2025-08-05 | Done | Low | 3
16 | TK-292 | Sophia | Backend | Leaderboard/Guild service: Inventory | Backend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-08-05 | 2025-08-06 | Done | High | 3
16 | TK-293 | Ava | Backend | Leaderboard/Guild service: Pet Companions | Backend task for 'Pet Companions'. Deliverable sized to 8 SP. | 2025-08-05 | 2025-08-09 | Done | Low | 8
16 | TK-294 | Liam | Data Team | Dashboard build: Season Pass | Data Team task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-08-06 | 2025-08-09 | Done | Critical | 5
16 | TK-295 | Sophia | Backend | API endpoint: Power-ups & Boosts | Backend task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-08-06 | 2025-08-08 | Done | Medium | 3
16 | TK-296 | Noah | Frontend | Implement UI: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-08-07 | 2025-08-10 | Done | Lowest | 5
16 | TK-297 | Michael | Backend | Leaderboard/Guild service: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-08-07 | 2025-08-08 | Done | High | 3
16 | TK-298 | Olivia | QA | Regression suite update: Obstacle Library | QA task for 'Obstacle Library'. Deliverable sized to 8 SP. | 2025-08-08 | 2025-08-12 | Done | Lowest | 8
16 | TK-299 | John | Business Analyst | Stakeholder workshop: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-08-09 | 2025-08-12 | Done | Critical | 5
16 | TK-300 | Alice | Business Analyst | Epic scoping: Inventory | Business Analyst task for 'Inventory'. Deliverable sized to 8 SP. | 2025-08-09 | 2025-08-13 | Done | Critical | 8
16 | TK-301 | Liam | Data Team | ETL pipeline: A/B Testing Framework | Data Team task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-08-09 | 2025-08-10 | Done | Medium | 3
16 | TK-302 | David | Frontend | Animations & VFX: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-08-09 | 2025-08-12 | Done | Medium | 5
16 | TK-303 | Emily | Frontend | UI integration test fixes: Inventory | Frontend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-08-10 | 2025-08-12 | Done | Critical | 3
16 | TK-304 | Daniel | QA | Test plan: Leaderboard | QA task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-08-10 | 2025-08-13 | Done | High | 8
16 | TK-305 | John | Business Analyst | Stakeholder workshop: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-08-10 | 2025-08-12 | Done | Medium | 5
16 | TK-306 | Michael | Backend | Authentication/Session: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-08-11 | 2025-08-12 | Done | Critical | 5
16 | TK-307 | Emily | Frontend | Responsive layout: Guilds & Chat | Frontend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-08-11 | 2025-08-12 | Done | Medium | 5
16 | TK-308 | Sophia | Backend | Authentication/Session: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-08-14 | 2025-08-16 | Done | Medium | 3
17 | TK-309 | Olivia | QA | Test plan: Social Sharing | QA task for 'Social Sharing'. Deliverable sized to 8 SP. | 2025-08-19 | 2025-08-22 | Done | Lowest | 8
17 | TK-310 | John | Business Analyst | User stories: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-08-19 | 2025-08-20 | Done | Medium | 5
17 | TK-311 | Liam | Data Team | A/B experiment design: Inventory | Data Team task for 'Inventory'. Deliverable sized to 8 SP. | 2025-08-19 | 2025-08-23 | Done | Low | 8
17 | TK-312 | Noah | Frontend | UX polish: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-08-20 | 2025-08-21 | Done | Critical | 5
17 | TK-313 | Sophia | Backend | Performance tuning: Core Runner Mechanics | Backend task for 'Core Runner Mechanics'. Deliverable sized to 8 SP. | 2025-08-22 | 2025-08-25 | Done | High | 8
17 | TK-314 | Michael | Backend | Performance tuning: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-08-22 | 2025-08-25 | Done | Critical | 5
17 | TK-315 | David | Frontend | UI integration test fixes: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-08-22 | 2025-08-25 | Done | Critical | 8
17 | TK-316 | Noah | Frontend | UI integration test fixes: Localization | Frontend task for 'Localization'. Deliverable sized to 3 SP. | 2025-08-23 | 2025-08-24 | Done | Lowest | 3
17 | TK-317 | Emily | Frontend | UX polish: A/B Testing Framework | Frontend task for 'A/B Testing Framework'. Deliverable sized to 8 SP. | 2025-08-23 | 2025-08-27 | Done | Low | 8
17 | TK-318 | Ava | Backend | Authentication/Session: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-08-23 | 2025-08-25 | Done | Critical | 3
17 | TK-319 | Michael | Backend | Game logic service: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-08-24 | 2025-08-26 | Done | Medium | 5
17 | TK-320 | Alice | Business Analyst | User stories: Character Customization | Business Analyst task for 'Character Customization'. Deliverable sized to 8 SP. | 2025-08-25 | 2025-08-27 | Done | Medium | 8
17 | TK-321 | Ava | Backend | Leaderboard/Guild service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-08-25 | 2025-08-26 | Done | Low | 5
17 | TK-322 | Daniel | QA | Test plan: Shop & IAP | QA task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-08-25 | 2025-08-27 | Done | Critical | 5
17 | TK-323 | John | Business Analyst | Stakeholder workshop: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-08-26 | 2025-08-28 | Done | Lowest | 3
17 | TK-324 | Daniel | QA | Functional test: Inventory | QA task for 'Inventory'. Deliverable sized to 3 SP. | 2025-08-26 | 2025-08-27 | Done | Lowest | 3
18 | TK-325 | David | Frontend | UI integration test fixes: Cloud Save | Frontend task for 'Cloud Save'. Deliverable sized to 8 SP. | 2025-09-02 | 2025-09-05 | Done | High | 8
18 | TK-326 | Michael | Backend | Authentication/Session: Cloud Save | Backend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-09-03 | 2025-09-05 | Done | Medium | 5
18 | TK-327 | Alice | Business Analyst | User stories: Guilds & Chat | Business Analyst task for 'Guilds & Chat'. Deliverable sized to 8 SP. | 2025-09-03 | 2025-09-05 | Done | Low | 8
18 | TK-328 | Olivia | QA | Exploratory testing: Power-ups & Boosts | QA task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-09-03 | 2025-09-05 | Done | Medium | 3
18 | TK-329 | John | Business Analyst | Acceptance criteria: Anti-cheat | Business Analyst task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-09-04 | 2025-09-05 | Done | High | 3
18 | TK-330 | Liam | Data Team | A/B experiment design: Beta Release | Data Team task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-09-04 | 2025-09-07 | Done | High | 5
18 | TK-331 | John | Business Analyst | Stakeholder workshop: Cloud Save | Business Analyst task for 'Cloud Save'. Deliverable sized to 3 SP. | 2025-09-04 | 2025-09-05 | Done | Critical | 3
18 | TK-332 | Noah | Frontend | UI integration test fixes: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-09-06 | 2025-09-07 | Done | High | 5
18 | TK-333 | Emily | Frontend | Implement UI: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-09-07 | 2025-09-09 | Done | Medium | 3
18 | TK-334 | Ava | Backend | API endpoint: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-09-07 | 2025-09-09 | Done | High | 3
18 | TK-335 | Liam | Data Team | A/B experiment design: Onboarding & Tutorial | Data Team task for 'Onboarding & Tutorial'. Deliverable sized to 5 SP. | 2025-09-08 | 2025-09-10 | Done | Critical | 5
18 | TK-336 | Sophia | Backend | Leaderboard/Guild service: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-09-08 | 2025-09-11 | Done | High | 8
18 | TK-337 | Daniel | QA | Test data setup: Crafting & Upgrades | QA task for 'Crafting & Upgrades'. Deliverable sized to 8 SP. | 2025-09-08 | 2025-09-11 | Done | Lowest | 8
18 | TK-338 | John | Business Analyst | Stakeholder workshop: Social Sharing | Business Analyst task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-09-08 | 2025-09-10 | Done | High | 3
18 | TK-339 | Olivia | QA | Test data setup: Push Notifications | QA task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-09-08 | 2025-09-10 | Done | Low | 5
18 | TK-340 | Ava | Backend | Authentication/Session: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-09-08 | 2025-09-09 | Done | Medium | 5
18 | TK-341 | Noah | Frontend | Animations & VFX: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-09-09 | 2025-09-10 | Done | High | 5
18 | TK-342 | Emily | Frontend | Implement UI: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-09-09 | 2025-09-10 | Done | Critical | 5
18 | TK-343 | Michael | Backend | Authentication/Session: Localization | Backend task for 'Localization'. Deliverable sized to 3 SP. | 2025-09-10 | 2025-09-12 | Done | High | 3
19 | TK-344 | Liam | Data Team | Dashboard build: Localization | Data Team task for 'Localization'. Deliverable sized to 8 SP. | 2025-09-15 | 2025-09-17 | Done | Lowest | 8
19 | TK-345 | Ava | Backend | Game logic service: Launch & Post-Launch | Backend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-09-15 | 2025-09-17 | Done | Critical | 5
19 | TK-346 | Sophia | Backend | Game logic service: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-09-15 | 2025-09-16 | Done | Medium | 5
19 | TK-347 | Ava | Backend | Performance tuning: Daily Challenges | Backend task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-09-15 | 2025-09-16 | Done | Critical | 5
19 | TK-348 | Sophia | Backend | Leaderboard/Guild service: A/B Testing Framework | Backend task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-09-16 | 2025-09-17 | Done | High | 3
19 | TK-349 | John | Business Analyst | Epic scoping: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-09-17 | 2025-09-18 | Done | Lowest | 3
19 | TK-350 | David | Frontend | Responsive layout: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-09-17 | 2025-09-19 | Done | High | 5
19 | TK-351 | Olivia | QA | Regression suite update: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 8 SP. | 2025-09-18 | 2025-09-22 | Done | High | 8
19 | TK-352 | Emily | Frontend | Responsive layout: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-09-19 | 2025-09-20 | Done | High | 5
19 | TK-353 | Michael | Backend | Authentication/Session: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-09-19 | 2025-09-22 | Done | Lowest | 5
19 | TK-354 | Noah | Frontend | UI integration test fixes: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-09-19 | 2025-09-22 | Done | Critical | 5
19 | TK-355 | David | Frontend | Implement UI: A/B Testing Framework | Frontend task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-09-20 | 2025-09-22 | Done | Lowest | 5
19 | TK-356 | Daniel | QA | Test data setup: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-09-20 | 2025-09-22 | Done | Low | 3
19 | TK-357 | John | Business Analyst | User stories: Leaderboard | Business Analyst task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-09-21 | 2025-09-24 | Done | Critical | 5
19 | TK-358 | Daniel | QA | Test data setup: Push Notifications | QA task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-09-21 | 2025-09-23 | Done | Critical | 3
19 | TK-359 | Alice | Business Analyst | Backlog refinement: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-09-21 | 2025-09-22 | Done | Medium | 5
19 | TK-360 | Emily | Frontend | Responsive layout: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-09-22 | 2025-09-24 | Done | Medium | 5
19 | TK-361 | Michael | Backend | Leaderboard/Guild service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-09-22 | 2025-09-25 | Done | Low | 5
19 | TK-362 | Noah | Frontend | Implement UI: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-09-24 | 2025-09-25 | Done | Low | 3
19 | TK-363 | Alice | Business Analyst | Epic scoping: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-09-24 | 2025-09-25 | Done | Lowest | 3
19 | TK-364 | Daniel | QA | Regression suite update: Localization | QA task for 'Localization'. Deliverable sized to 3 SP. | 2025-09-24 | 2025-09-26 | Done | High | 3
20 | TK-365 | Olivia | QA | Functional test: Inventory | QA task for 'Inventory'. Deliverable sized to 3 SP. | 2025-09-29 | 2025-09-30 | Done | Critical | 3
20 | TK-366 | Ava | Backend | Authentication/Session: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-09-29 | 2025-10-02 | Ready to work | Medium | 5
20 | TK-367 | Liam | Data Team | Balance analysis: Obstacle Library | Data Team task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-09-29 | 2025-10-01 | Ready to work | Lowest | 5
20 | TK-368 | Michael | Backend | Performance tuning: Guilds & Chat | Backend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-09-29 | 2025-10-02 | To Do | Critical | 5
20 | TK-369 | Sophia | Backend | Leaderboard/Guild service: Social Sharing | Backend task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-09-30 | 2025-10-01 | Ready to work | Medium | 3
20 | TK-370 | Sophia | Backend | Performance tuning: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-10-01 | 2025-10-02 | To Do | High | 5
20 | TK-371 | Daniel | QA | Test plan: Live Ops Tooling | QA task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-10-01 | 2025-10-02 | Done | High | 5
20 | TK-372 | David | Frontend | UI integration test fixes: Inventory | Frontend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-10-02 | 2025-10-03 | Ready for Test | Lowest | 3
20 | TK-373 | John | Business Analyst | Acceptance criteria: Localization | Business Analyst task for 'Localization'. Deliverable sized to 3 SP. | 2025-10-03 | 2025-10-04 | Ready for Test | Medium | 3
20 | TK-374 | John | Business Analyst | Stakeholder workshop: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-10-03 | 2025-10-06 | Done | High | 5
20 | TK-375 | Emily | Frontend | UI integration test fixes: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 8 SP. | 2025-10-03 | 2025-10-05 | Ready for Test | Medium | 8
20 | TK-376 | Olivia | QA | Regression suite update: Weekly Boss Chase | QA task for 'Weekly Boss Chase'. Deliverable sized to 3 SP. | 2025-10-03 | 2025-10-04 | Done | Critical | 3
20 | TK-377 | Olivia | QA | Regression suite update: Onboarding & Tutorial | QA task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-10-05 | 2025-10-06 | In Progress | Medium | 3
20 | TK-378 | Ava | Backend | API endpoint: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-10-05 | 2025-10-07 | Testing | High | 5
20 | TK-379 | David | Frontend | UX polish: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-10-06 | 2025-10-08 | Done | Lowest | 3
20 | TK-380 | Alice | Business Analyst | Acceptance criteria: Shop & IAP | Business Analyst task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-10-06 | 2025-10-09 | Testing | Medium | 5
20 | TK-381 | Michael | Backend | API endpoint: Guilds & Chat | Backend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-10-06 | 2025-10-07 | Ready for Test | Low | 5
20 | TK-382 | David | Frontend | Animations & VFX: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-10-07 | 2025-10-08 | Ready to work | High | 3
20 | TK-383 | Daniel | QA | Exploratory testing: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-10-07 | 2025-10-09 | Testing | Lowest | 5
20 | TK-384 | Noah | Frontend | Implement UI: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-10-07 | 2025-10-09 | Ready to work | Low | 5
20 | TK-385 | Alice | Business Analyst | User stories: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-10-07 | 2025-10-09 | Testing | Low | 5
20 | TK-386 | Noah | Frontend | Implement UI: Inventory | Frontend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-10-08 | 2025-10-09 | Done | Low | 3
20 | TK-387 | Liam | Data Team | ETL pipeline: Accessibility | Data Team task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-10-09 | 2025-10-11 | In Progress | Low | 3
21 | TK-388 | Olivia | QA | Exploratory testing: Beta Release | QA task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-10-13 | 2025-10-14 | To Do | Low | 5
21 | TK-389 | Liam | Data Team | Balance analysis: Weekly Boss Chase | Data Team task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-10-13 | 2025-10-14 | In Progress | High | 5
21 | TK-390 | Olivia | QA | Test data setup: Power-ups & Boosts | QA task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-10-13 | 2025-10-15 | Done | Critical | 3
21 | TK-391 | Alice | Business Analyst | Stakeholder workshop: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-10-14 | 2025-10-17 | Ready to work | Medium | 5
21 | TK-392 | Emily | Frontend | Implement UI: Level Generator | Frontend task for 'Level Generator'. Deliverable sized to 3 SP. | 2025-10-15 | 2025-10-17 | Done | Low | 3
21 | TK-393 | John | Business Analyst | Backlog refinement: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-10-15 | 2025-10-16 | Ready to work | Lowest | 3
21 | TK-394 | David | Frontend | UI integration test fixes: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-10-16 | 2025-10-18 | In Progress | Lowest | 3
21 | TK-395 | Daniel | QA | Functional test: Inventory | QA task for 'Inventory'. Deliverable sized to 8 SP. | 2025-10-17 | 2025-10-20 | Testing | Lowest | 8
21 | TK-396 | John | Business Analyst | Epic scoping: Accessibility | Business Analyst task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-10-17 | 2025-10-19 | To Do | Lowest | 3
21 | TK-397 | Sophia | Backend | Performance tuning: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-10-18 | 2025-10-21 | Blocked | Lowest | 5
21 | TK-398 | David | Frontend | UI integration test fixes: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-10-18 | 2025-10-19 | Blocked | High | 5
21 | TK-399 | Sophia | Backend | Authentication/Session: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-10-19 | 2025-10-20 | To Do | Critical | 5
21 | TK-400 | Noah | Frontend | UX polish: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 8 SP. | 2025-10-19 | 2025-10-24 | Ready to work | Critical | 8
21 | TK-401 | Emily | Frontend | Implement UI: Localization | Frontend task for 'Localization'. Deliverable sized to 5 SP. | 2025-10-19 | 2025-10-21 | To Do | Critical | 5
21 | TK-402 | Michael | Backend | Game logic service: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-10-20 | 2025-10-21 | In Progress | Critical | 5
21 | TK-403 | Ava | Backend | API endpoint: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-10-20 | 2025-10-24 | Ready to work | Critical | 8
21 | TK-404 | John | Business Analyst | Stakeholder workshop: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-10-21 | 2025-10-23 | Ready to work | Medium | 3
21 | TK-405 | Michael | Backend | Performance tuning: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-10-21 | 2025-10-22 | Ready to work | Critical | 5
21 | TK-406 | Alice | Business Analyst | User stories: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-10-23 | 2025-10-25 | To Do | High | 3
21 | TK-407 | Liam | Data Team | A/B experiment design: Accessibility | Data Team task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-10-23 | 2025-10-24 | In Progress | High | 3
22 | TK-408 | Olivia | QA | Functional test: Daily Challenges | QA task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-10-27 | 2025-10-29 | In Progress | Low | 5
22 | TK-409 | Noah | Frontend | Implement UI: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-10-27 | 2025-10-29 | Ready for Test | Medium | 5
22 | TK-410 | Noah | Frontend | UX polish: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-10-28 | 2025-10-29 | In Progress | High | 3
22 | TK-411 | Michael | Backend | Game logic service: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-10-28 | 2025-10-29 | Done | Medium | 3
22 | TK-412 | David | Frontend | Responsive layout: Localization | Frontend task for 'Localization'. Deliverable sized to 3 SP. | 2025-10-29 | 2025-10-30 | To Do | High | 3
22 | TK-413 | Liam | Data Team | Balance analysis: Crafting & Upgrades | Data Team task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-10-30 | 2025-11-02 | To Do | Low | 5
22 | TK-414 | Alice | Business Analyst | User stories: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 5 SP. | 2025-10-30 | 2025-11-02 | To Do | Critical | 5
22 | TK-415 | Alice | Business Analyst | Stakeholder workshop: Accessibility | Business Analyst task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-10-30 | 2025-10-31 | Done | Lowest | 3
22 | TK-416 | Emily | Frontend | UI integration test fixes: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 8 SP. | 2025-10-30 | 2025-11-04 | To Do | Low | 8
22 | TK-417 | Ava | Backend | Performance tuning: Cloud Save | Backend task for 'Cloud Save'. Deliverable sized to 8 SP. | 2025-10-31 | 2025-11-04 | To Do | Low | 8
22 | TK-418 | Daniel | QA | Exploratory testing: Localization | QA task for 'Localization'. Deliverable sized to 3 SP. | 2025-11-01 | 2025-11-02 | To Do | Low | 3
22 | TK-419 | Olivia | QA | Test data setup: Anti-cheat | QA task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-11-02 | 2025-11-04 | To Do | Lowest | 3
22 | TK-420 | John | Business Analyst | Acceptance criteria: Shop & IAP | Business Analyst task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-11-02 | 2025-11-07 | To Do | Critical | 8
22 | TK-421 | Daniel | QA | Exploratory testing: Social Sharing | QA task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-11-03 | 2025-11-04 | To Do | High | 5
22 | TK-422 | David | Frontend | Responsive layout: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-11-03 | 2025-11-05 | To Do | High | 3
22 | TK-423 | Sophia | Backend | Performance tuning: Cloud Save | Backend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-11-03 | 2025-11-06 | To Do | Medium | 5
22 | TK-424 | Sophia | Backend | Performance tuning: Onboarding & Tutorial | Backend task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-11-04 | 2025-11-06 | To Do | Critical | 3
22 | TK-425 | David | Frontend | UX polish: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-11-04 | 2025-11-05 | To Do | Lowest | 3
22 | TK-426 | Michael | Backend | API endpoint: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-11-04 | 2025-11-07 | To Do | Lowest | 5
22 | TK-427 | Liam | Data Team | Event schema: Live Ops Tooling | Data Team task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-11-06 | 2025-11-07 | To Do | Lowest | 3
23 | TK-428 | David | Frontend | Responsive layout: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-11-10 | 2025-11-13 | To Do | Lowest | 5
23 | TK-429 | Emily | Frontend | UX polish: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-11-11 | 2025-11-15 | To Do | Medium | 8
23 | TK-430 | Noah | Frontend | Implement UI: Daily Challenges | Frontend task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-11-11 | 2025-11-13 | To Do | Low | 3
23 | TK-431 | Noah | Frontend | Animations & VFX: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-11-11 | 2025-11-14 | To Do | Lowest | 5
23 | TK-432 | Daniel | QA | Regression suite update: Obstacle Library | QA task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-11-12 | 2025-11-13 | To Do | Low | 3
23 | TK-433 | Alice | Business Analyst | Epic scoping: Core Runner Mechanics | Business Analyst task for 'Core Runner Mechanics'. Deliverable sized to 5 SP. | 2025-11-12 | 2025-11-13 | To Do | Lowest | 5
23 | TK-434 | Daniel | QA | Test data setup: Level Generator | QA task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-11-12 | 2025-11-15 | To Do | Medium | 5
23 | TK-435 | David | Frontend | Animations & VFX: Guilds & Chat | Frontend task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-11-13 | 2025-11-15 | To Do | Lowest | 3
23 | TK-436 | Liam | Data Team | ETL pipeline: Pet Companions | Data Team task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-11-14 | 2025-11-16 | To Do | Medium | 3
23 | TK-437 | Sophia | Backend | Leaderboard/Guild service: Localization | Backend task for 'Localization'. Deliverable sized to 5 SP. | 2025-11-15 | 2025-11-17 | To Do | Lowest | 5
23 | TK-438 | Ava | Backend | Authentication/Session: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-11-16 | 2025-11-17 | To Do | Critical | 3
23 | TK-439 | Michael | Backend | Game logic service: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 8 SP. | 2025-11-16 | 2025-11-21 | To Do | Medium | 8
23 | TK-440 | Olivia | QA | Regression suite update: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-11-16 | 2025-11-19 | To Do | Medium | 5
23 | TK-441 | John | Business Analyst | Backlog refinement: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-11-17 | 2025-11-19 | To Do | Medium | 5
23 | TK-442 | Sophia | Backend | Authentication/Session: Onboarding & Tutorial | Backend task for 'Onboarding & Tutorial'. Deliverable sized to 5 SP. | 2025-11-17 | 2025-11-19 | To Do | Critical | 5
23 | TK-443 | Olivia | QA | Test plan: A/B Testing Framework | QA task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-11-18 | 2025-11-21 | To Do | Critical | 5
23 | TK-444 | Ava | Backend | Authentication/Session: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-11-18 | 2025-11-19 | To Do | Low | 5
23 | TK-445 | Liam | Data Team | ETL pipeline: Analytics & Telemetry | Data Team task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-11-18 | 2025-11-19 | To Do | Lowest | 5
23 | TK-446 | John | Business Analyst | Acceptance criteria: Obstacle Library | Business Analyst task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-11-18 | 2025-11-19 | To Do | Critical | 3
23 | TK-447 | Alice | Business Analyst | Acceptance criteria: Leaderboard | Business Analyst task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-11-19 | 2025-11-20 | To Do | Low | 3
24 | TK-448 | David | Frontend | UX polish: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 8 SP. | 2025-11-24 | 2025-11-29 | To Do | Critical | 8
24 | TK-449 | Ava | Backend | Performance tuning: Analytics & Telemetry | Backend task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-11-25 | 2025-11-26 | To Do | High | 5
24 | TK-450 | Noah | Frontend | Responsive layout: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 8 SP. | 2025-11-25 | 2025-11-30 | To Do | Lowest | 8
24 | TK-451 | Ava | Backend | Authentication/Session: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-11-26 | 2025-11-29 | To Do | Low | 5
24 | TK-452 | John | Business Analyst | Stakeholder workshop: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-11-27 | 2025-11-29 | To Do | Lowest | 5
24 | TK-453 | Liam | Data Team | Dashboard build: Power-ups & Boosts | Data Team task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-11-27 | 2025-11-30 | To Do | High | 5
24 | TK-454 | Alice | Business Analyst | Stakeholder workshop: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 8 SP. | 2025-11-28 | 2025-12-03 | To Do | Low | 8
24 | TK-455 | Sophia | Backend | Game logic service: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-11-28 | 2025-12-01 | To Do | Critical | 8
24 | TK-456 | Liam | Data Team | Balance analysis: Offline Mode | Data Team task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-11-29 | 2025-12-01 | To Do | High | 5
24 | TK-457 | Emily | Frontend | UX polish: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-11-29 | 2025-12-01 | To Do | Low | 5
24 | TK-458 | Emily | Frontend | Animations & VFX: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-11-29 | 2025-11-30 | To Do | Medium | 3
24 | TK-459 | Daniel | QA | Regression suite update: Character Customization | QA task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-11-29 | 2025-12-02 | To Do | Critical | 5
24 | TK-460 | John | Business Analyst | Epic scoping: Season Pass | Business Analyst task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-11-30 | 2025-12-02 | To Do | Low | 3
24 | TK-461 | Daniel | QA | Regression suite update: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-11-30 | 2025-12-03 | To Do | Lowest | 5
24 | TK-462 | Michael | Backend | Leaderboard/Guild service: Cloud Save | Backend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-11-30 | 2025-12-03 | To Do | Lowest | 5
24 | TK-463 | Olivia | QA | Functional test: Shop & IAP | QA task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-11-30 | 2025-12-04 | To Do | High | 8
24 | TK-464 | Michael | Backend | Leaderboard/Guild service: A/B Testing Framework | Backend task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-12-02 | 2025-12-03 | To Do | Low | 3
25 | TK-465 | Ava | Backend | Leaderboard/Guild service: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-12-08 | 2025-12-10 | To Do | High | 5
25 | TK-466 | David | Frontend | Implement UI: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-12-09 | 2025-12-12 | To Do | Lowest | 5
25 | TK-467 | Liam | Data Team | ETL pipeline: Push Notifications | Data Team task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-12-09 | 2025-12-10 | To Do | Critical | 3
25 | TK-468 | Sophia | Backend | Performance tuning: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-12-09 | 2025-12-12 | To Do | High | 5
25 | TK-469 | Olivia | QA | Test data setup: Pet Companions | QA task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-12-10 | 2025-12-12 | To Do | Critical | 3
25 | TK-470 | Michael | Backend | Performance tuning: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-12-10 | 2025-12-13 | To Do | Critical | 5
25 | TK-471 | Olivia | QA | Test plan: Shop & IAP | QA task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-12-10 | 2025-12-13 | To Do | Lowest | 5
25 | TK-472 | Ava | Backend | Game logic service: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-12-11 | 2025-12-13 | To Do | Critical | 3
25 | TK-473 | Sophia | Backend | Game logic service: Power-ups & Boosts | Backend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-12-12 | 2025-12-13 | To Do | Medium | 5
25 | TK-474 | Daniel | QA | Regression suite update: Character Customization | QA task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-12-12 | 2025-12-14 | To Do | Critical | 3
25 | TK-475 | Alice | Business Analyst | Stakeholder workshop: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-12-13 | 2025-12-15 | To Do | High | 5
25 | TK-476 | Daniel | QA | Exploratory testing: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-12-13 | 2025-12-14 | To Do | Lowest | 3
25 | TK-477 | Noah | Frontend | Responsive layout: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-12-13 | 2025-12-15 | To Do | Low | 3
25 | TK-478 | Noah | Frontend | Responsive layout: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-12-14 | 2025-12-17 | To Do | Medium | 5
25 | TK-479 | John | Business Analyst | Acceptance criteria: Power-ups & Boosts | Business Analyst task for 'Power-ups & Boosts'. Deliverable sized to 8 SP. | 2025-12-14 | 2025-12-16 | To Do | Critical | 8
25 | TK-480 | Liam | Data Team | Balance analysis: Live Ops Tooling | Data Team task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-12-14 | 2025-12-17 | To Do | Critical | 5
25 | TK-481 | Emily | Frontend | Animations & VFX: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-12-14 | 2025-12-15 | To Do | Lowest | 3
25 | TK-482 | Daniel | QA | Test data setup: Level Generator | QA task for 'Level Generator'. Deliverable sized to 3 SP. | 2025-12-15 | 2025-12-17 | To Do | Critical | 3
25 | TK-483 | David | Frontend | UX polish: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-12-15 | 2025-12-16 | To Do | Low | 3
25 | TK-484 | Alice | Business Analyst | Backlog refinement: Live Ops Tooling | Business Analyst task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-12-16 | 2025-12-17 | To Do | Critical | 5
25 | TK-485 | Emily | Frontend | Animations & VFX: Level Generator | Frontend task for 'Level Generator'. Deliverable sized to 3 SP. | 2025-12-17 | 2025-12-19 | To Do | Medium | 3
25 | TK-486 | Emily | Frontend | Animations & VFX: Daily Challenges | Frontend task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-12-18 | 2025-12-19 | To Do | Low | 3
25 | TK-487 | Michael | Backend | Leaderboard/Guild service: Pet Companions | Backend task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-12-18 | 2025-12-19 | To Do | Lowest | 3
26 | TK-488 | Michael | Backend | Performance tuning: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-12-22 | 2025-12-23 | To Do | Low | 3
26 | TK-489 | David | Frontend | UX polish: Weekly Boss Chase | Frontend task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-12-24 | 2025-12-25 | To Do | High | 5
26 | TK-490 | Liam | Data Team | A/B experiment design: Analytics & Telemetry | Data Team task for 'Analytics & Telemetry'. Deliverable sized to 8 SP. | 2025-12-24 | 2025-12-29 | To Do | Lowest | 8
26 | TK-491 | David | Frontend | Implement UI: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-12-24 | 2025-12-26 | To Do | Lowest | 5
26 | TK-492 | Daniel | QA | Test data setup: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-12-25 | 2025-12-27 | To Do | Lowest | 5
26 | TK-493 | Olivia | QA | Test plan: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-12-25 | 2025-12-26 | To Do | High | 5
26 | TK-494 | Alice | Business Analyst | Acceptance criteria: Core Runner Mechanics | Business Analyst task for 'Core Runner Mechanics'. Deliverable sized to 8 SP. | 2025-12-25 | 2025-12-29 | To Do | Low | 8
26 | TK-495 | Daniel | QA | Functional test: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-12-26 | 2025-12-27 | To Do | Low | 5
26 | TK-496 | Emily | Frontend | Implement UI: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-12-27 | 2025-12-30 | To Do | Medium | 5
26 | TK-497 | Michael | Backend | Authentication/Session: Social Sharing | Backend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-12-27 | 2025-12-29 | To Do | Medium | 5
26 | TK-498 | Emily | Frontend | UX polish: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-12-27 | 2025-12-30 | To Do | Lowest | 5
26 | TK-499 | Olivia | QA | Regression suite update: Anti-cheat | QA task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-12-28 | 2025-12-29 | To Do | Critical | 5
26 | TK-500 | Ava | Backend | Game logic service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-12-29 | 2025-12-31 | To Do | High | 5
26 | TK-501 | Sophia | Backend | Leaderboard/Guild service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-12-29 | 2025-12-31 | To Do | Lowest | 8
26 | TK-502 | Noah | Frontend | Animations & VFX: Daily Challenges | Frontend task for 'Daily Challenges'. Deliverable sized to 8 SP. | 2025-12-29 | 2026-01-01 | To Do | High | 8
26 | TK-503 | John | Business Analyst | Acceptance criteria: Power-ups & Boosts | Business Analyst task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-12-30 | 2026-01-01 | To Do | High | 5
26 | TK-504 | John | Business Analyst | Stakeholder workshop: Accessibility | Business Analyst task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-12-30 | 2026-01-02 | To Do | Low | 5
26 | TK-505 | Ava | Backend | API endpoint: Inventory | Backend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-12-30 | 2026-01-01 | To Do | Lowest | 5